## S00_Index
S00 — WORKBOOK INDEX — Greenfield Expansion Phase II · CapEx & Supply Chain Portfolio Model
Prepared by: Sourabh Tarodekar ¦ Contact: sourabh232@gmail.com ¦ Purpose: Portfolio demonstration of Engineering Program Management – CapEx & Supply Chain Operations
This workbook contains synthetic sample data created for portfolio demonstration purposes only. The data does not represent proprietary or confidential information from any employer or client.
ZONE LEGEND — TAB COLOR GUIDE
Zone | Color | Category | Purpose
Zone 0 | Gray | Navigation & Governance | Index, Disclaimer & Assumptions, version control
Zone 1 | Blue | Program Foundation | Equipment portfolio, supplier data, should-cost, TCO
Zone 2 | Green | Planning & Scheduling | WBS, CPM, Milestone Roadmap, deployment, capacity, demand forecast
Zone 3 | Orange | Financial & Risk | AR, cash flow, FX, scenario analysis, supply chain risk
Zone 4 | Purple | Strategic Supply Chain | Market analysis, network, sourcing, dual-source, negotiation, inventory, assets
Zone 5 | Red | Execution & Control | Gates, ECO, VDC, yield metrics, ROI tracker, scorecard, change tracker
Zone 6 | Teal | Portfolio & Capital Allocation | Multi-program register, portfolio dashboard, prioritization scorecard
SHEET DIRECTORY
Sheet # | Sheet Name (click to navigate) | Zone | Status | What This Sheet Demonstrates | Key Metrics / Outputs
S00 | S00_Index | Zone 0 | New | Workbook navigation, zone guide, sheet directory | This page
S01 | S01_Disclaimer_Assumptions | Zone 0 | Revised | Portfolio disclaimer, global model assumptions, version control | WACC=8%, Uptime=92%, FX rates, version log
S02 | S02_Equipment_Portfolio | Zone 1 | Revised | Master equipment dataset for 2 programs (PRG-001, PRG-002) — costs, energy, throughput | $13.87M + $2.38M CapEx across 21 platforms
S03 | S03_Supplier_Dataset | Zone 1 | Revised | Supplier lead times, reliability scores, risk tiers across both programs | 21 OEMs; Program ID column for portfolio rollups
S04 | S04_Should_Cost_Model | Zone 1 | Preserved | First-principles should-cost by material, labour, OH, margin | Should-cost vs quote variance analysis
S05 | S05_TCO_Downtime_Model | Zone 1 | Preserved | 10-year TCO, energy, maintenance, downtime cost comparison | NPV-based lifecycle cost comparison
S06 | S06_WBS | Zone 2 | New | Work Breakdown Structure — all program workstreams and tasks | 8 workstreams, 60+ work packages
S07 | S07_CPM_Master_Schedule | Zone 2 | New | Critical Path Method schedule — activities, float, predecessors | Critical path = 46 weeks; 39 activities
S08 | S08_Program_Milestone_Roadmap | Zone 2 | New | Visual Gantt-style program roadmap — recruiter-friendly view | G0 to G5 gates, Apr-2025 to Dec-2025
S09 | S09_Deployment_Timeline | Zone 2 | Revised | Equipment-level deployment schedule by workstream | 46-week program; 6 critical-path items
S10 | S10_Capacity_Planning | Zone 2 | Revised | Equipment capacity model — throughput, utilization, bottleneck ID | 1,040K units/yr capacity; 72.1% utilization
S11 | S11_Demand_Forecast | Zone 2 | New | Time-series demand forecast with scenario banding and accuracy tracking | 750K baseline; 2023-2025 ramp model
S12 | S12_AR_Summary | Zone 3 | Revised | Formal capital appropriations request — Phase II budget & approval | $16.062M AR; 14.2% IRR; 4.2yr payback
S13 | S13_Scenario_Analysis | Zone 3 | Revised | Scenario A/B/C comparison — CapEx, OpEx, NPV tradeoffs | Scenario B recommended; $40.04M benchmark
S14 | S14_CashFlow_Model | Zone 3 | New | Merged monthly + quarterly cash flow with S-curve profile | $14.42M program spend; compressed to 2025
S15 | S15_FX_Exposure_Model | Zone 3 | Revised | EUR/JPY FX risk — baseline, adverse, favorable scenarios | 9/10 line items hedged
S16 | S16_Supply_Chain_Risk | Zone 3 | Revised | Supply chain risk heatmap — 25 components across both programs, 4 risk tiers | 7 CRITICAL; 4 HIGH; single-source analysis
S17 | S17_Supply_Market_Analysis | Zone 4 | New | Supply market structure — concentration, players, pricing trends | 8 commodities; HHI analysis; price trends
S18 | S18_Supply_Chain_Network | Zone 4 | New | Logistics network map — supplier geography, routes, Tier 2 visibility | 15 suppliers; transit times; customs data
S19 | S19_Strategic_Sourcing_Pipeline | Zone 4 | New | Full sourcing workflow — RFI to award, contract status, savings | 12 categories tracked
S20 | S20_Dual_MultiSource_Strategy | Zone 4 | New | Dual/multi-source program — qualification status, risk reduction | 8 commodities; 3 active qual programs
S21 | S21_Negotiation_Tracker | Zone 4 | New | Commercial negotiation log — targets, BATNA, outcomes, savings | 10 negotiations; $537K confirmed savings
S22 | S22_Capacity_Supplier_Facing | Zone 4 | New | Supplier capacity assessment — program share, flex, MOQ, buffer | 15 suppliers; capacity constraint analysis
S23 | S23_Inventory_Buffer_Planning | Zone 4 | New | Inventory strategy — raw materials, WIP, spares, safety stock | $124.2K spare parts inventory value
S24 | S24_Asset_Tracking | Zone 4 | New | Physical asset register — location, status, lifecycle, warranty | 45 assets; installation dates; replacement plan
S25 | S25_Milestone_Gate_Tracker | Zone 5 | Revised | Phase-gate program tracker — G0 to G5 gates, criteria, blockers | G0+G1 approved; G2-G5 in progress
S26 | S26_Engineering_Change_Orders | Zone 5 | New | Formal ECO register — origin, scope, cost/schedule impact, approval | 10 ECOs; $107.2K cost impact
S27 | S27_Vendor_Design_Changes | Zone 5 | New | Supplier-initiated design change log — disposition, requalification | 7 VDCs; risk-assessed; approval tracked
S28 | S28_Yield_Production_Metrics | Zone 5 | New | OEE, yield, defect tracking by process tool and period | 96% target yield; OEE model by equipment
S29 | S29_Equipment_ROI_Tracker | Zone 5 | Revised | Post-commissioning actual vs plan — throughput, uptime, revenue impact | 30/90/180-day checkpoints; variance analysis
S30 | S30_Executive_Dashboard | Zone 0 | Revised | Executive KPI summary — all zones linked, recruiter first view | All key metrics; zone navigation prompts
S31 | S31_Vendor_Scorecard | Zone 5 | New | Weighted vendor scorecard — delivery, quality, commercial, technical | 18 suppliers scored; 4 Preferred, 9 Approved
S32 | S32_Change_Tracker | Zone 5 | New | Engineering change management log — cost, schedule, risk | 12 CRs; $210.5K cost impact; 5.8% contingency used
S33 | S33_Portfolio_Register | Zone 6 | New | Multi-program register — one row per program, live-linked financials & risk | 2 programs; PRG-001 Greenfield, PRG-002 Riverside
S34 | S34_Portfolio_Dashboard | Zone 6 | New | Portfolio-wide KPI rollup across all active/proposed programs | Total portfolio CapEx, blended risk, program comparison
S35 | S35_Portfolio_Prioritization | Zone 6 | New | Weighted capital allocation scorecard — ranks programs for sequencing | Greenfield #1 (4.25/5.0), Riverside #2 (3.15/5.0)

## S34_Portfolio_Dashboard
S34 — PORTFOLIO EXECUTIVE DASHBOARD — ALL PROGRAMS
Portfolio Director: Sourabh Tarodekar · Aggregates every active/proposed program in S33_Portfolio_Register · All values linked live
PORTFOLIO KEY PERFORMANCE INDICATORS
ACTIVE + PROPOSED PROGRAMS |  | TOTAL PORTFOLIO CAPEX |  | TOTAL APPROVED/EST. BUDGET |  | BLENDED SUPPLY CHAIN RISK |  | TOTAL EQUIPMENT PLATFORMS
S33 — Portfolio Register |  | Sum across all programs |  | Incl. contingency + reserves |  | Avg across all programs |  | All programs combined
PROGRAM-BY-PROGRAM COMPARISON
Program | Phase / Status | CapEx (USD) | % of Portfolio CapEx | Approved/Est. Budget (USD) | IRR | Risk Score | Equipment Platforms | Payback (yrs)
PORTFOLIO TOTAL |  |  | 100%
PORTFOLIO NOTES
PRG-001 (Greenfield Expansion Phase II) is fully approved and in execution — every figure above is live-linked to its 33-sheet model (S00-S32). PRG-002 (Riverside Automation Upgrade Phase I) is at FEL-2 (feasibility); its equipment, supplier, and risk data are live-linked to S02/S03/S16, but its IRR/NPV/payback are Finance's FEL-2 planning estimates pending a full TCO build-out ahead of AR submission. See S35_Portfolio_Prioritization for the capital allocation decision framework across both programs.

## S33_Portfolio_Register
S33 — Portfolio Register — All Active & Proposed CapEx Programs
Portfolio Director: Sourabh Tarodekar ¦ One row per program; financial and risk fields link live to each program's own data sheets (S02, S03, S16) where a supporting model exists ¦ Program ID is the join key used across S33-S35
Program ID | Program Name | Sponsor | Program Manager | Business Unit | Phase / Gate | Status | Total CapEx — Equip+Install (USD) | Contingency Reserve (USD) | Total Approved Budget (USD) | Estimated IRR | 10-Yr NPV (USD) | Payback (yrs) | Avg Supply Chain Risk Score | Equipment Platforms | Strategic Capacity Impact | Notes
PRG-001 | Greenfield Expansion Phase II | Sourabh Tarodekar (Portfolio Director) | Sourabh Tarodekar | Semiconductor & Advanced Process Division | G2 — Equipment Build & FAT (Execution) | APPROVED — IN EXECUTION | [5 empty] | 4.2 |  |  | +312,000 units/yr (35% customer volume increase) | Full 33-sheet model (S00-S32); financials, schedule, and risk fully linked
PRG-002 | Riverside Automation Upgrade Phase I | Sourabh Tarodekar (Portfolio Director) | Elena Vargas | Packaging & Distribution Operations | FEL-2 — Feasibility (Pre-Execution) | PROPOSED — AWAITING AR APPROVAL |  |  |  | 16.8% | 1850000 | 3.1 |  |  | +18% packaging line throughput (~45,000 cases/day incremental) | Equipment/supplier/risk data live-linked (S02, S03, S16); IRR/NPV/payback are Finance FEL-2 estimates, not yet a full 10-yr TCO model
PORTFOLIO TOTALS
Active + Proposed Programs
Total Portfolio CapEx (USD)
Total Portfolio Approved/Estimated Budget (USD)
Blended Avg Supply Chain Risk Score
Total Equipment Platforms (All Programs)

## S35_Portfolio_Prioritization
S35 — Portfolio Prioritization — Capital Allocation Decision Framework
Portfolio Director: Sourabh Tarodekar ¦ Weighted scorecard used to rank active + proposed programs each planning cycle ¦ Same weighting methodology as S13_Scenario_Analysis, applied program-vs-program instead of scenario-vs-scenario
SCORING DIMENSION WEIGHTS & RATIONALE
Dimension | Weight | PRG-001 Score (1-5) | PRG-002 Score (1-5) | Wtd PRG-001 | Wtd PRG-002 | Rationale
Financial Return (NPV / IRR) | 25% | 5 | 3 |  |  | Greenfield's $9.5M NPV and 14.2% IRR dwarf Riverside's $1.85M/16.8% in absolute terms
Strategic Fit / Business Priority | 20% | 5 | 3 |  |  | Greenfield is core capacity for the primary revenue driver; Riverside is an efficiency play
Supply Chain / Execution Risk (higher score = lower risk) | 15% | 3 | 4 |  |  | Greenfield carries a HIGH-tier single-source pump risk; Riverside's risk profile is materially lighter
Schedule Readiness / Time to Value | 15% | 4 | 2 |  |  | Greenfield is already at G2 execution; Riverside is still FEL-2, pre-AR
Capital Efficiency (impact per $ requested) | 15% | 3 | 4 |  |  | Riverside's smaller ask and 3.1-yr payback are more capital-efficient than Greenfield's $16M ask
Organizational Readiness | 10% | 5 | 3 |  |  | Greenfield has a dedicated, established program team; Riverside's PM and team are still standing up
TOTAL WEIGHTED SCORE
RECOMMENDED SEQUENCING
#1 Ranked Program
#1 Weighted Score
DECISION SUMMARY
Greenfield Expansion Phase II ranks #1 (4.25/5.0) and remains the portfolio's priority commitment — it is already AR-approved and in execution, and no action changes that. Riverside Automation Upgrade Phase I ranks #2 (3.15/5.0): recommend continuing FEL-2 feasibility work and targeting AR submission once Greenfield's peak capital draw (Q3-2025, per S14_CashFlow_Model) has passed, so the two programs' spend curves don't compete for the same capital window. Riverside's lower risk profile and faster payback make it an attractive next-in-queue candidate once schedule and organizational readiness catch up to Greenfield's.

## S01_Disclaimer_Assumptions
S01 — Disclaimer & Global Model Assumptions
Program: Greenfield Expansion Phase II ¦ All hardcoded inputs are in BLUE — update here ONLY. All other sheets link to this sheet.
This workbook contains synthetic sample data created for portfolio demonstration purposes only. The data does not represent proprietary or confidential information from any employer or client. Prepared by Sourabh Tarodekar for demonstration of Engineering Program Management – CapEx & Supply Chain Operations capabilities. Contact: sourabh232@gmail.com
ENERGY & UTILITIES
Parameter | Value | Unit | Source / Basis | Date Validated | Notes
Energy Price – Electricity | 11% | USD/kWh | EIA Industrial Rate Survey – US Avg 2024 | 2025-01 | Used in Annual Energy Cost calculations across S02, S05 TCO model
Natural Gas Price | 4.8 | USD/MMBtu | EIA Natural Gas Industrial Price – 2024 | 2025-01 | Used for high-temp furnace operating cost estimation
Cooling Water Cost | 1.8% | USD/gallon | Site Utility Rate Schedule Rev C | 2025-01 | Applicable to chiller and process cooling loads
N2 Bulk Gas Cost | 4.5% | USD/scf | Site Utility Rate Schedule Rev C | 2025-01 | Applicable to gas handling system operating cost
FINANCIAL & DISCOUNT ASSUMPTIONS
Parameter | Value | Unit | Source / Basis | Date Validated | Notes
Discount Rate (WACC) | 8% | — | Finance Department; WACC model approved Q4-2024 | 2025-01 | Used in NPV calculations; 8% reflects blended cost of capital
Project Horizon | 10 | Years | Standard CapEx lifecycle policy | 2025-01 | All TCO and NPV models use 10-year horizon
Tax Rate (Effective) | 21% | — | US Federal + State blended estimate | 2025-01 | Applied in AR payback model for after-tax IRR
CapEx Depreciation Method | MACRS 7-yr | — | Finance / Tax Counsel guidance | 2025-01 | Per AR Summary financial justification
Inflation Rate | 2.5% | — | Corporate finance planning assumption | 2025-01 | Used to escalate Year 2-10 OpEx in TCO model
LABOR RATES
Parameter | Value | Unit | Source / Basis | Date Validated | Notes
Fabrication Shop Rate | 95 | USD/hr | Supplier benchmarking; 2024 MW industrial rate | 2025-01 | Used in Should-Cost labor model (S04)
Engineering Labor Rate | 120 | USD/hr | Internal engineering rate card Rev 2024 | 2025-01 | Used in NRE and program labor estimates
Installation Labor Rate | 85 | USD/hr | Facilities contractor rate card | 2025-01 | Used in on-site installation cost estimates
Field Service Rate (Supplier) | 175 | USD/hr | Supplier FSE rate benchmark | 2025-01 | Used in downtime / MTTR cost modelling
EQUIPMENT PERFORMANCE
Parameter | Value | Unit | Source / Basis | Date Validated | Notes
Equipment Uptime Target | 92% | — | Program engineering specification | 2025-01 | 92% uptime = 608 downtime hrs/yr basis for MTBF model
Planned Maintenance Downtime | 4% | — | Maintenance planning schedule | 2025-01 | 4% of annual hours allocated to preventive maintenance
Process Yield Assumption | 96% | — | Engineering process spec | 2025-01 | Used in capacity model to calculate effective throughput
Production Value per Hour | 4500 | USD/hr | Finance — fully-loaded production cost model | 2025-01 | Downtime Cost = Value/hr × MTTR hrs
SUPPLIER COST MODEL INPUTS
Parameter | Value | Unit | Source / Basis | Date Validated | Notes
Supplier Margin – Low | 15% | — | Benchmarking; competitive-bid suppliers | 2025-01 | Lower bound; applied to multi-source components
Supplier Margin – High | 25% | — | Benchmarking; sole-source suppliers | 2025-01 | Upper bound; applied to single-source components
Material Scrap Factor – Low | 5% | — | Engineering; precision machined parts | 2025-01 | 5% scrap on raw material purchases
Material Scrap Factor – High | 8% | — | Engineering; cast / welded assemblies | 2025-01 | 8% scrap on complex fabrications
Material Price – Steel (304 SS) | 3.8 | USD/kg | Metal bulletin Q1-2025 | 2025-01 | Used in vacuum chamber and furnace body cost estimates
Material Price – Aluminum | 4.2 | USD/kg | Metal bulletin Q1-2025 | 2025-01 | Used in robotics frame and structural components
Material Price – Copper | 9.5 | USD/kg | COMEX spot Q1-2025 | 2025-01 | Used in transformer winding and electrical bus cost estimates
DEPLOYMENT TIMELINE ASSUMPTIONS
Parameter | Value | Unit | Source / Basis | Date Validated | Notes
Supplier Manufacturing Duration | 20 | Weeks | Program schedule baseline Rev 1.0 | 2025-01 | Range: 16–24 wks depending on equipment complexity
Factory Acceptance Testing (FAT) | 2 | Weeks | Standard FAT protocol – all equipment | 2025-01 | 2 weeks minimum; may extend for complex systems
International Shipping Duration | 3 | Weeks | Freight forwarder estimate; ocean freight | 2025-01 | Air freight contingency +50% cost; used for risk scenario
On-Site Installation | 4 | Weeks | Facilities project plan Rev A | 2025-01 | Per equipment platform; parallel installation possible
Utility Hookup | 2 | Weeks | Facilities electrical + mechanical schedule | 2025-01 | Includes inspection and commissioning sign-off
Process Qualification (PQ) | 5 | Weeks | Process engineering qualification plan | 2025-01 | Range: 4–6 wks; 5 wks used as baseline
FX SENSITIVITY ASSUMPTIONS
Parameter | Value | Unit | Source / Basis | Date Validated | Notes
USD/EUR Exchange Rate (Baseline) | 1.09 | USD per EUR | Bloomberg rates Q1-2025 average | 2025-01 | Baseline conversion rate for EUR-denominated equipment
USD/JPY Exchange Rate (Baseline) | 149.5 | JPY per USD | Bloomberg rates Q1-2025 average | 2025-01 | Baseline conversion rate for JPY-denominated equipment
EUR Sensitivity – Adverse | 1.15 | USD per EUR | FX stress scenario +6% | 2025-01 | 1% move in EUR/USD = ~$85K portfolio cost impact
EUR Sensitivity – Favorable | 1.03 | USD per EUR | FX stress scenario -6% | 2025-01 | Favorable scenario used in S13 Scenario Analysis
JPY Sensitivity – Adverse | 142 | JPY per USD | FX stress scenario (JPY strengthens) | 2025-01 | Stronger JPY = higher USD cost for JPY equipment
JPY Sensitivity – Favorable | 157 | JPY per USD | FX stress scenario (JPY weakens) | 2025-01 | Weaker JPY = lower USD cost for JPY equipment
VERSION CONTROL LOG — Model Revision History & Change Tracking
Version | Date | Owner / Author | Change Description | Impact on Model | Approval Status | Notes / Reference
V1.0 | 2025-02-10 | Sourabh Tarodekar (TPM) | Initial workbook created. Equipment portfolio dataset populated with 15 platforms from supplier quotes. | Baseline established. All formulas reference V1.0 assumptions. | APPROVED | Baseline model — AR-2025-0082 submission basis
V1.1 | 2025-02-14 | S. Kim (Supply Chain) | Updated Pfeiffer vacuum pump (EQ-002) lead time from 16 to 26 weeks based on supplier confirmation. | Deployment timeline extended. EQ-002 now on critical path. Risk flag updated to CRITICAL. | APPROVED | Supplier email confirmation 2025-02-13 on file
V1.2 | 2025-02-18 | R. Patel (Finance) | Discount rate updated from 7.5% to 8.0% per Q1-2025 corporate WACC guidance. | NPV reduced by ~$420K. TCO model and scenario analysis recalculated. | APPROVED | Finance guidance memo FIN-2025-007
V1.3 | 2025-02-24 | T. Okonkwo (Facilities) | Added EQ-004 crane hire and floor reinforcement to installation cost — +$62K. | Total installation cost increased. CR-001 raised. Change tracker updated. | APPROVED | CR-001 approved by PM 2025-02-24
V1.4 | 2025-03-05 | M. Chen (Process Eng.) | Equipment uptime revised from 90% to 92% following process engineering specification review. | Annual capacity increased. Utilization % reduced. Capacity model updated. | APPROVED | Process spec document PE-2025-014 Rev A
V1.5 | 2025-03-10 | R. Patel (Finance) | FX sensitivity assumptions added. EUR/JPY baseline and stress scenarios populated. | FX exposure model now active. EUR/USD baseline 1.09, JPY/USD baseline 149.5. | APPROVED | Bloomberg rates Q1-2025 average
V1.6 | 2025-03-17 | S. Kim (Supply Chain) | Supplier risk scores recalculated after Daifuku confirmed 30-week manufacturing lead time for EQ-006. | EQ-006 risk tier escalated to CRITICAL. Supply chain risk index increased. | APPROVED | Daifuku PO confirmation email
V1.7 | 2025-03-19 | Sourabh Tarodekar (TPM) | AR Summary populated and submitted to VP Engineering + CFO. Budget: $40.04M (Scenario B benchmark). | Formal program approval process initiated. Model frozen for AR submission. | APPROVED | AR-2025-0082 submitted to Finance
V1.8 | 2025-04-05 | R. Patel (Finance) | AR approved. POs placed for long-lead items. Spend tracking model activated. | Program execution phase begins. Cash flow schedule now active. | APPROVED | CFO approval email 2025-04-05
V1.9 | 2025-05-12 | P. Singh (IT/OT) | IT/OT DMZ infrastructure cost ($45K) added to scope. CR-009 raised. | Contingency draw of $45K. Change tracker updated. Contingency at 5.8%. | UNDER REVIEW | CR-009 pending PM approval
V2.0 | 2025-05-19 | Sourabh Tarodekar (TPM) | Version 2.0 release: Cash flow schedule, FX exposure model, and ROI tracker sheets added. | Workbook extended with 4 new analytical sheets. Full model refresh completed. | APPROVED | Issued to Finance and Engineering Leadership

## S02_Equipment_Portfolio
S02 — CapEx Equipment Portfolio Dataset — Advanced Manufacturing Program
Fiscal Year: 2025 ¦ Portfolio Director: Sourabh Tarodekar ¦ Status: Active ¦ Blue = Hardcoded Input · Black = Formula · Green = Cross-sheet Link ¦ Program ID column (right-most) enables portfolio-wide SUMIFS rollups in S33-S35
Equip. ID | Category | Tool Type / Model | Supplier | Region | Ccy | Unit Cost (USD) | Qty | Total Equip. Cost (USD) | Install Cost/Unit (USD) | Install Total (USD) | Life (yrs) | Energy (kWh/hr) | Annual Maint. Rate (%) | Throughput (u/hr) | Op Hrs/Yr | Annual Energy Cost (USD) | Engineering Notes | Program ID
EQ-001 | Vacuum Pump System | Dry Screw Vacuum Pump – 250 m³/hr | Edwards Vacuum | UK | EUR | 185000 | 4 |  | 22000 |  | 12 | 18.5 | 6% | 0 | 8320 |  | Requires N2 purge line; facility electrical upgrade needed prior to installation | PRG-001
EQ-002 | Vacuum Pump System | Turbomolecular Pump Assembly – 2000 L/s | Pfeiffer Vacuum | DE | EUR | 310000 | 3 |  | 28000 |  | 10 | 12 | 5% | 0 | 8320 |  | Single-source supplier; no qualified alt vendor as of Q1-2025; lead time under review | PRG-001
EQ-003 | High-Temp Furnace | Tube Furnace System – 1200°C / 8-zone | Thermco Systems | USA | USD | 520000 | 2 |  | 45000 |  | 15 | 95 | 4% | 24 | 8320 |  | FAT to be conducted at supplier site in Austin, TX; includes process recipe transfer | PRG-001
EQ-004 | High-Temp Furnace | Batch Oxidation Furnace – 1100°C | Tokyo Electron Ltd | JP | JPY | 680000 | 2 |  | 52000 |  | 15 | 110 | 4.5% | 18 | 8320 |  | JPY-denominated; FX hedge required; import duty ~3.2%; installation requires crane lift | PRG-001
EQ-005 | Robotics / Automation | 6-Axis Wafer Transfer Robot – SCARA | Brooks Automation | USA | USD | 275000 | 6 |  | 18000 |  | 10 | 4.2 | 5% | 120 | 8320 |  | Software integration with fab MES required; vendor to supply integration team on-site | PRG-001
EQ-006 | Robotics / Automation | Overhead Track Conveyor – 50m loop | Daifuku | JP | JPY | 420000 | 1 |  | 85000 |  | 12 | 22 | 4% | 0 | 8320 |  | Single installation; civil works for track mounts included in install cost estimate | PRG-001
EQ-007 | Gas Handling System | Process Gas Cabinet – 6-zone manifold | Air Liquide Engineering | FR | EUR | 195000 | 4 |  | 32000 |  | 12 | 0.8 | 6% | 0 | 8320 |  | Hazmat classified; requires local regulatory permit; supplier quote under negotiation | PRG-001
EQ-008 | Gas Handling System | Bulk Gas Storage & Delivery – N2/O2/Ar | Linde Engineering | DE | EUR | 340000 | 1 |  | 120000 |  | 20 | 2.5 | 3% | 0 | 8320 |  | Facility infrastructure tie-in; utility coordination required with site civil team | PRG-001
EQ-009 | PLC Control System | Distributed Control System – Siemens S7-1500 | Siemens AG | DE | EUR | 165000 | 5 |  | 15000 |  | 10 | 1.2 | 7% | 0 | 8320 |  | Software license included; annual subscription renewal at $12K/system; cybersecurity review pending | PRG-001
EQ-010 | PLC Control System | SCADA Integration Platform – Ignition | Inductive Automation | USA | USD | 85000 | 3 |  | 8000 |  | 8 | 0.5 | 8% | 0 | 8320 |  | Server hardware separate line item; IT/OT network segmentation required by InfoSec | PRG-001
EQ-011 | Facility Infra – Power | Dry-Type Transformer – 2 MVA / 480V | ABB Ltd | CH | USD | 210000 | 2 |  | 35000 |  | 25 | 0 | 2% | 0 | 8760 |  | Component reused from prior program (legacy); refurbishment cost included in install | PRG-001
EQ-012 | Facility Infra – Cooling | Process Chiller System – 200 kW | Daikin Applied | JP | JPY | 295000 | 3 |  | 40000 |  | 15 | 68 | 5% | 0 | 8760 |  | Glycol loop design pending; coordinate with mechanical engineering; JPY FX risk noted | PRG-001
EQ-013 | Vacuum Pump System | Roots Blower Booster – 500 m³/hr | Busch Vacuum | DE | EUR | 125000 | 6 |  | 14000 |  | 10 | 28 | 6% | 0 | 8320 |  | Paired with EQ-001 dry screw pumps; interdependent installation sequence required | PRG-001
EQ-014 | High-Temp Furnace | RTP – Rapid Thermal Processor | Applied Materials | USA | USD | 875000 | 2 |  | 60000 |  | 12 | 85 | 4% | 32 | 8320 |  | Highest unit cost item; finance approval gate required before PO issuance; AR pending | PRG-001
EQ-015 | Robotics / Automation | AMR Fleet – Autonomous Mobile Robots (×10) | Mobile Industrial Robots (MiR) | DK | EUR | 380000 | 1 |  | 45000 |  | 8 | 6 | 6% | 0 | 8320 |  | Fleet management software license included; Wi-Fi infrastructure upgrade required | PRG-001
PRG-001 TOTAL — Greenfield Expansion Phase II
PRG-001 SUMMARY STATISTICS — Greenfield Expansion Phase II
Total Equipment Purchase Cost (USD)
Total Installation Cost (USD)
Total Portfolio CapEx (USD)
Total Annual Energy Cost (USD)
Number of Equipment Platforms
Total Equipment Units
Average Unit Cost (USD)
Highest Unit Cost Item (USD)
PRG-002 EQUIPMENT — Riverside Automation Upgrade Phase I
Equip. ID | Category | Tool Type / Model | Supplier | Region | Ccy | Unit Cost (USD) | Qty | Total Equip. Cost (USD) | Install Cost/Unit (USD) | Install Total (USD) | Life (yrs) | Energy (kWh/hr) | Annual Maint. Rate (%) | Throughput (u/hr) | Op Hrs/Yr | Annual Energy Cost (USD) | Engineering Notes | Program ID
RV-001 | Robotics / Automation | Palletizing Robot – 6-Axis, 40kg payload | Fanuc America | USA | USD | 165000 | 2 |  | 20000 |  | 10 | 3.8 | 5% | 0 | 6240 |  | Replaces manual end-of-line palletizing; guarding and safety scanner included in install | PRG-002
RV-002 | Packaging Automation | Case Packer / Cartoning System | Krones AG | DE | EUR | 410000 | 1 |  | 55000 |  | 12 | 14 | 5% | 0 | 6240 |  | Single-source specialized cartoning technology; no qualified alt vendor identified | PRG-002
RV-003 | Robotics / Automation | AGV Fleet – Tow/Unit Load (×6) | Fetch Robotics | USA | USD | 85000 | 6 |  | 8000 |  | 8 | 1.1 | 6% | 0 | 6240 |  | Fleet management software license included; warehouse Wi-Fi survey required pre-deployment | PRG-002
RV-004 | Quality / Automation | Vision Inspection System (×3) | Cognex Corporation | USA | USD | 62000 | 3 |  | 6000 |  | 8 | 0.6 | 4% | 0 | 6240 |  | In-line case/label inspection; integrates with existing MES via OPC-UA | PRG-002
RV-005 | PLC Control System | Warehouse Control System Integration | Rockwell Automation | USA | USD | 145000 | 1 |  | 25000 |  | 10 | 1 | 6% | 0 | 6240 |  | Integrates AGV fleet, conveyor, and WMS; software license + 1yr support included | PRG-002
RV-006 | Material Handling | Conveyor & Sortation System | Dematic Corp | USA | USD | 520000 | 1 |  | 95000 |  | 15 | 26 | 4% | 0 | 6240 |  | Longest lead item; civil floor anchoring required; phased cutover to avoid line downtime | PRG-002
PRG-002 TOTAL — Riverside Automation Upgrade Phase I

## S03_Supplier_Dataset
S03 — Supplier & Supply Chain Dataset — Advanced Manufacturing CapEx Program
Last Updated: 2025-Q3 ¦ Owner: Supply Chain / Sourcing Team ¦ Risk Score = (Current LT ÷ Standard LT) × (100 − Reliability Score) ¦ Risk Tier: LOW < 5 ¦ MODERATE 5–15 ¦ HIGH > 15 ¦ Program ID column enables portfolio-wide rollups
Supplier | Component Type | Equip. Ref | Region | Ccy | Std LT (wks) | Current LT (wks) | LT Delta (wks) | Reliability (0-100) | Single Source Risk | Alt Supplier Available | Calc. Risk Score | Risk Tier | Engineering Notes | Program ID
Edwards Vacuum | Dry Screw Vacuum Pumps | EQ-001 | UK | EUR | 14 | 18 |  | 82 | No | Yes |  |  | Reliability impacted by post-Brexit logistics; alt vendor pre-qual in progress with Busch | PRG-001
Pfeiffer Vacuum | Turbomolecular Pumps | EQ-002 | DE | EUR | 16 | 26 |  | 88 | Yes | No |  |  | CRITICAL – single source; no qualified alternative; EQ-002 delivery risk HIGH; escalate to program director | PRG-001
Thermco Systems | High-Temp Tube Furnaces | EQ-003 | USA | USD | 18 | 20 |  | 91 | No | Yes |  |  | Preferred supplier; strong historical performance; alt supplier (BTU International) pre-qualified | PRG-001
Tokyo Electron Ltd (TEL) | Batch Oxidation Furnaces | EQ-004 | JP | JPY | 20 | 28 |  | 85 | No | Yes |  |  | JPY currency risk; FX hedge executed Q4-2024; alt: Kokusai Electric pre-qualified | PRG-001
Brooks Automation | Wafer Transfer Robots (SCARA) | EQ-005 | USA | USD | 12 | 14 |  | 90 | No | Yes |  |  | Software integration complexity is primary risk; not supply risk; support SLA confirmed | PRG-001
Daifuku | Overhead Conveyor Track System | EQ-006 | JP | JPY | 22 | 30 |  | 83 | Yes | No |  |  | Single source for overhead track design; civil interface drawings required 8 wks prior to FAT | PRG-001
Air Liquide Engineering | Process Gas Cabinets | EQ-007 | FR | EUR | 16 | 22 |  | 79 | No | Yes |  |  | Quote under negotiation; delivery risk moderate; Matheson Gas alt supplier evaluated | PRG-001
Linde Engineering | Bulk Gas Storage & Delivery | EQ-008 | DE | EUR | 24 | 32 |  | 86 | No | Yes |  |  | Long procurement cycle; requires site permit coordination; 32-wk lead time confirmed by supplier | PRG-001
Siemens AG | Distributed Control Systems | EQ-009 | DE | EUR | 10 | 14 |  | 92 | No | Yes |  |  | Strong supply reliability; cybersecurity review adds 3-wk internal approval cycle | PRG-001
Inductive Automation | SCADA Platform Licenses | EQ-010 | USA | USD | 4 | 5 |  | 95 | No | Yes |  |  | Software license only; low supply risk; primary risk is IT/OT integration complexity | PRG-001
ABB Ltd | Dry-Type Transformers | EQ-011 | CH | USD | 14 | 20 |  | 87 | No | Yes |  |  | Component partially reused from prior program; new units on 20-wk market lead time | PRG-001
Daikin Applied | Process Chiller Systems | EQ-012 | JP | JPY | 16 | 20 |  | 89 | No | Yes |  |  | Glycol loop interface drawings required prior to FAT; JPY exposure monitored | PRG-001
Busch Vacuum | Roots Blower Boosters | EQ-013 | DE | EUR | 12 | 15 |  | 88 | No | Yes |  |  | Paired supply with Edwards EQ-001; coordinated delivery schedule required | PRG-001
Applied Materials | Rapid Thermal Processors (RTP) | EQ-014 | USA | USD | 20 | 24 |  | 90 | No | Yes |  |  | Highest value item; supplier requires 30% deposit at PO; finance pre-approval required | PRG-001
Mobile Industrial Robots (MiR) | AMR Fleet – 10 Units | EQ-015 | DK | EUR | 14 | 18 |  | 84 | No | Yes |  |  | Fleet SW license bundled; Wi-Fi site survey required 6 wks pre-installation | PRG-001
PRG-001 SUPPLY CHAIN RISK SUMMARY — Greenfield Expansion Phase II
Avg Standard Lead Time (wks)
Avg Current Lead Time (wks)
Avg Lead Time Delta (wks)
Avg Reliability Score (0-100)
Avg Calculated Risk Score
Max Risk Score (Worst Supplier)
# Single-Source Components
# Components with Alt Supplier
# HIGH Risk Tier Suppliers
PRG-002 SUPPLIERS — Riverside Automation Upgrade Phase I
Supplier | Component Type | Equip. Ref | Region | Ccy | Std LT (wks) | Current LT (wks) | LT Delta (wks) | Reliability (0-100) | Single Source Risk | Alt Supplier Available | Calc. Risk Score | Risk Tier | Engineering Notes | Program ID
Fanuc America | Palletizing Robots | RV-001 | USA | USD | 10 | 12 |  | 91 | No | Yes |  |  | Deep bench of qualified integrators; low supply risk; standard robot platform | PRG-002
Krones AG | Case Packer / Cartoning Systems | RV-002 | DE | EUR | 20 | 24 |  | 86 | Yes | No |  |  | Single-source specialized cartoning technology; no qualified alternative identified | PRG-002
Fetch Robotics | AGV Fleet Units | RV-003 | USA | USD | 8 | 9 |  | 93 | No | Yes |  |  | Mature AGV platform; Locus Robotics evaluated as viable alternate | PRG-002
Cognex Corporation | Vision Inspection Systems | RV-004 | USA | USD | 6 | 7 |  | 95 | No | Yes |  |  | Commodity machine-vision hardware; Keyence pre-qualified as alternate | PRG-002
Rockwell Automation | Warehouse Control System | RV-005 | USA | USD | 8 | 9 |  | 94 | No | Yes |  |  | Strong integrator relationship; low supply risk; standard PlantPAx platform | PRG-002
Dematic Corp | Conveyor & Sortation Systems | RV-006 | USA | USD | 16 | 20 |  | 88 | No | Yes |  |  | Complex site-specific integration; Honeywell Intelligrated evaluated as alternate | PRG-002
PRG-002 SUPPLY CHAIN RISK SUMMARY — Riverside Automation Upgrade Phase I
Avg Calculated Risk Score
Max Risk Score (Worst Supplier)
# Single-Source Components
# HIGH Risk Tier Suppliers

## S04_Should_Cost_Model
S04 — First-Principles Should-Cost Model — Advanced Manufacturing Capital Equipment
Clean-sheet cost build-up per equipment category ¦ All inputs in BLUE ¦ Formulas in BLACK ¦ Cross-sheet links in GREEN ¦ Independent cost estimate used to challenge supplier quotes and identify cost reduction opportunities.
Equipment Category | Cost Element | Mat. Wt (kg) | Mat. Price (USD/kg) | Mat. Cost | Labor Hrs | Shop Rate | Labor Cost | Subcomp/Electronics | Sub-Total | Overhead (12%) | Supplier Margin | TOTAL Cost | Notes
Vacuum Pump System | Raw Material – Stainless Steel Body | 280 | 3.8 |  | 0 | 0 |  | 0 |  |  |  |  | Precision-cast SS housing; 304SS at market rate
Vacuum Pump System | Machining & Fabrication Labor | 0 | 0 |  | 95 |  |  | 0 |  |  |  |  | CNC turning & milling; pump body, rotor, stator components
Vacuum Pump System | Purchased Subcomponents – Seals/Bearings | 0 | 0 |  | 0 | 0 |  | 18500 |  |  |  |  | Ceramic bearings, PTFE seals, shaft seals; sourced from FAG/SKF
Vacuum Pump System | Electronics & Motor Drive System | 0 | 0 |  | 0 | 0 |  | 22000 |  |  |  |  | VFD drive, PLC I/O cards, HMI touchscreen, wiring harness
Vacuum Pump System | Assembly Labor | 0 | 0 |  | 32 |  |  | 0 |  |  |  |  | Final assembly, alignment, internal leak test; 32 hrs per unit
Vacuum Pump System | Quality / Acceptance Testing | 0 | 0 |  | 12 |  |  | 0 |  |  |  |  | Performance characterization, helium leak test, ultimate pressure verification
High-Temp Furnace | Raw Material – Inconel / Quartz / Refractory | 420 | 6.84 |  | 0 | 0 |  | 0 |  |  |  |  | Inconel 625 hot zone; quartz liner; ceramic refractory bricks
High-Temp Furnace | Machining & Fabrication Labor | 0 | 0 |  | 180 |  |  | 0 |  |  |  |  | Welding, machining, tube bending; complex multi-zone fabrication
High-Temp Furnace | Purchased Subcomponents – Heating Elements | 0 | 0 |  | 0 | 0 |  | 45000 |  |  |  |  | SiC heating elements, 8-zone; Kanthal A1 backup; sourced from Kanthal
High-Temp Furnace | Electronics & Control Systems | 0 | 0 |  | 0 | 0 |  | 38000 |  |  |  |  | Multi-zone PID controllers, SCR power units, thermocouple arrays
High-Temp Furnace | Assembly Labor | 0 | 0 |  | 65 |  |  | 0 |  |  |  |  | Zone assembly, insulation packing, wiring, pre-commissioning
High-Temp Furnace | Quality / Acceptance Testing | 0 | 0 |  | 20 |  |  | 0 |  |  |  |  | Temperature uniformity survey (9-point), ramp rate validation, atmosphere leak test
Robotics / Automation | Raw Material – Aluminum Frame & Structure | 85 | 4.2 |  | 0 | 0 |  | 0 |  |  |  |  | 6061 AL structural extrusions, machined joints, end-effector blanks
Robotics / Automation | Machining & Fabrication Labor | 0 | 0 |  | 40 |  |  | 0 |  |  |  |  | CNC machining of end-effectors, links, flanges; anodizing finish
Robotics / Automation | Purchased Subcomponents – Servo / Drive Train | 0 | 0 |  | 0 | 0 |  | 52000 |  |  |  |  | Harmonic drive reducers, servo motors, encoders; Yaskawa / Nabtesco
Robotics / Automation | Electronics & Vision System | 0 | 0 |  | 0 | 0 |  | 28000 |  |  |  |  | Robot controller, teach pendant, vision camera + lighting, safety scanner
Robotics / Automation | Software & Integration | 0 | 0 |  | 35 |  |  | 0 |  |  |  |  | MES/SEMI interface SW development, recipe upload, FAT validation scripts
Robotics / Automation | Quality / Acceptance Testing | 0 | 0 |  | 10 |  |  | 0 |  |  |  |  | Path accuracy, repeatability ±0.05mm, cycle time validation, safety relay test
Gas Handling System | Raw Material – 316L SS Tubing & Fittings | 60 | 4.56 |  | 0 | 0 |  | 0 |  |  |  |  | 316L EP-grade tubing, VCR fittings, valves; electropolished internal surfaces
Gas Handling System | Machining & Fabrication Labor | 0 | 0 |  | 55 |  |  | 0 |  |  |  |  | Tube bending, orbital welding, manifold assembly; cleanroom fabrication
Gas Handling System | Purchased Subcomponents – Valves & Regulators | 0 | 0 |  | 0 | 0 |  | 32000 |  |  |  |  | Swagelok/Parker pneumatic valves, MFCs, pressure regulators, check valves
Gas Handling System | Electronics & Safety Interlock System | 0 | 0 |  | 0 | 0 |  | 18000 |  |  |  |  | Gas detection sensors, PLC safety relays, solenoid driver cards, HMI
Gas Handling System | Assembly & Leak Testing | 0 | 0 |  | 28 |  |  | 0 |  |  |  |  | Assembly, helium leak test (<1E-9 atm·cc/s), pressure hold test, passivation
Gas Handling System | Quality / Acceptance Testing | 0 | 0 |  | 8 |  |  | 0 |  |  |  |  | Gas purity validation, flow calibration, emergency shutoff functional test
PLC Control System | Purchased Subcomponents – PLC Hardware | 0 | 0 |  | 0 | 0 |  | 42000 |  |  |  |  | Siemens S7-1500 CPU, I/O cards, power supplies, HMI panel; list price
PLC Control System | Panel Fabrication & Wiring | 0 | 0 |  | 45 |  |  | 0 |  |  |  |  | Control panel fabrication, DIN rail mounting, cable management, labeling
PLC Control System | Software Development & Programming | 0 | 0 |  | 80 |  |  | 0 |  |  |  |  | Ladder logic/FBD development, HMI graphics, alarm management, I/O mapping
PLC Control System | Factory Acceptance Testing | 0 | 0 |  | 16 |  |  | 0 |  |  |  |  | FAT protocol execution, point-to-point I/O check, interlock simulation
SHOULD-COST SUMMARY BY EQUIPMENT CATEGORY
Equipment Category | Material Cost | Labor Cost | Subcomponents | Sub-Total | Overhead (12%) | Supplier Margin | TOTAL Should-Cost | Supplier Quote (Budget Est.) | Variance (Quote-SC) | Variance %
Vacuum Pump System | [7 empty] | 195000
High-Temp Furnace | [7 empty] | 540000
Robotics / Automation | [7 empty] | 285000
Gas Handling System | [7 empty] | 205000
PLC Control System | [7 empty] | 175000
GRAND TOTAL

## S05_TCO_Downtime_Model
S05 — Total Cost of Ownership (TCO) & Downtime Risk Model — 10-Year Lifecycle Analysis
Compares Supplier A (Premium — TEL/AMAT-type) vs Supplier B (Value — domestic alternative) across purchase, energy, maintenance, downtime, and lifecycle NPV ¦ Discount Rate from S01_Disclaimer_Assumptions
MODEL PARAMETERS (linked from S01_Disclaimer_Assumptions)
Discount Rate (WACC)
Project Horizon (Years) | 10
Energy Price (USD/kWh)
Production Value per Hour (USD/hr)
Inflation Rate
EQUIPMENT COMPARISON — SUPPLIER A (PREMIUM) vs SUPPLIER B (VALUE)
Cost Parameter | Supplier A (Premium) | Supplier B (Value) | Delta (B-A) | Notes
Purchase Price (per unit, USD) | 680000 | 520000 |  | Supplier A = TEL EQ-004 type; Supplier B = domestic alternative
Quantity | 2 | 2 |  | Equal quantity for fair comparison
Installation Cost (per unit, USD) | 52000 | 38000 |  | Supplier A requires specialized installation crew (JPY contract)
Energy Consumption (kWh/hr) | 110 | 98 |  | Supplier A higher thermal efficiency spec; Supplier B 11% higher power draw
Operational Hours (Annual) | 8320 | 8320 |  | Both operate on identical shift schedule
Maintenance Rate (% of purchase) | 4.5% | 5.5% |  | Supplier A lower maint rate; Supplier B higher due to older platform design
Expected MTBF (hrs) | 4200 | 2800 |  | Mean Time Between Failures; Supplier A more robust platform
Expected MTTR (hrs) | 6 | 10 |  | Mean Time To Repair; Supplier A has faster FSE response SLA
Spare Parts Annual Cost (USD) | 18000 | 28000 |  | Supplier A proprietary spares expensive but fewer events; B more frequent
Expected Equipment Lifetime (yrs) | 15 | 12 |  | Supplier A longer qualified life; Supplier B 12 yr basis
Residual Value at End of Life (%) | 5% | 3% |  | Estimated salvage/residual as % of purchase price
10-YEAR LIFECYCLE COST MODEL
Cost Component / Supplier | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10 | 10-Yr Total | NPV (10-Yr)
1. Purchase Cost (total)
Supplier A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Supplier B |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
2. Installation Cost (total)
Supplier A |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
Supplier B |  | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
3. Annual Energy Cost (escalates with inflation from Year 2)
Supplier A
Supplier B
4. Annual Maintenance Cost (% of purchase; escalates with inflation)
Supplier A
Supplier B
5. Annual Spare Parts Cost (escalates with inflation)
Supplier A
Supplier B
6. Downtime Cost (Annual) — (Op Hrs ÷ MTBF) × MTTR × Production Value/hr
Supplier A
Supplier B
TOTAL COST OF OWNERSHIP SUMMARY
Supplier | Y1 | Y2 | Y3 | Y4 | Y5 | Y6 | Y7 | Y8 | Y9 | Y10 | 10-Yr Total | NPV (10-Yr)
A (Premium)
B (Value)
TCO DELTA (B Savings vs A)

## S06_WBS
S06 — Work Breakdown Structure (WBS) — Greenfield Expansion Phase II
Program: Greenfield Expansion Phase II ¦ Owner: Sourabh Tarodekar ¦ Status: Active ¦ All dates 2025 ¦ WBS hierarchy: Level 1 = Program ¦ Level 2 = Workstream ¦ Level 3 = Work Package ¦ WBS codes used as Activity IDs in S07_CPM_Master_Schedule
WBS Code | Level | Workstream / Work Package | Responsible Function | Duration Est (wks) | Start Wk | End Wk | Deliverable / Exit Criterion
1.0 | 1 | GREENFIELD EXPANSION PHASE II — PROGRAM | Program Management | 46 | 1 | 46 | Full program from AR approval to production release
1.1 | 2 | PROGRAM MANAGEMENT | Program Management | 46 | 1 | 46 | Program governance and control
1.1.1 | 3 | Program kick-off & AR execution | PM / Finance | 1 | 1 | 1 | AR signed, cost centre open, PO authority issued
1.1.2 | 3 | Stakeholder communication plan | PM / Eng Leadership | 1 | 1 | 2 | RACI matrix, communication cadence agreed
1.1.3 | 3 | Program schedule baseline | PM / Scheduling | 1 | 1 | 2 | CPM schedule issued, baseline locked
1.1.4 | 3 | Weekly program review cadence | PM | 45 | 2 | 46 | Weekly status reports issued throughout program
1.1.5 | 3 | Lessons learned & close-out report | PM | 1 | 46 | 46 | Program close-out document issued
1.2 | 2 | SOURCING & PROCUREMENT | Supply Chain / Sourcing | 14 | 1 | 14 | All long-lead POs placed; contracts executed
1.2.1 | 3 | RFQ issue — long-lead equipment (EQ-002,004,008,014) | Sourcing | 1 | 1 | 1 | RFQs issued to shortlisted suppliers
1.2.2 | 3 | Supplier commercial evaluation & BAFO | Sourcing | 2 | 1 | 3 | Bid tabulations complete; BAFO received
1.2.3 | 3 | Negotiation & contract award — EQ-014 (AMAT RTP) | Sourcing / Legal | 2 | 2 | 4 | PO issued; 30% deposit paid
1.2.4 | 3 | Negotiation & contract award — EQ-002 (Pfeiffer TMP) | Sourcing / Legal | 2 | 2 | 4 | PO issued; FX hedge confirmed
1.2.5 | 3 | Negotiation & contract award — EQ-004 (TEL Furnace) | Sourcing / Legal | 2 | 2 | 4 | PO issued; JPY hedge executed
1.2.6 | 3 | Negotiation & contract award — remaining equipment | Sourcing | 2 | 3 | 5 | All remaining POs placed
1.2.7 | 3 | FX forward contract execution — EUR & JPY | Finance / Treasury | 1 | 3 | 4 | Hedge contracts in place before PO placement
1.2.8 | 3 | Import/export documentation package | Logistics / Trade Compliance | 2 | 4 | 6 | HS codes filed; import bonds arranged
1.2.9 | 3 | Shimadzu alt-source qualification initiation (EQ-002) | Sourcing / Engineering | 8 | 4 | 12 | Alt vendor qual program started; TMP-3203L under test
1.3 | 2 | ENGINEERING | Engineering / Process | 20 | 1 | 20 | Design freeze; FAT specifications issued
1.3.1 | 3 | Equipment technical specification review | Process / Mech Eng | 2 | 1 | 3 | Supplier specs signed off; deviation log issued
1.3.2 | 3 | FAT protocol development — all equipment | Process Engineering | 3 | 2 | 5 | FAT protocols issued; supplier acceptance
1.3.3 | 3 | Utility design package — electrical, gas, cooling | Facilities Engineering | 4 | 2 | 6 | Utility design drawings issued for civil/mech
1.3.4 | 3 | Site layout & equipment placement plan | Facilities / Mech Eng | 3 | 3 | 6 | Final floor plan approved; civil works can start
1.3.5 | 3 | Integration spec — MES/SCADA/DCS | Controls / IT-OT | 4 | 3 | 7 | Integration design spec issued and approved
1.3.6 | 3 | Process recipe transfer — TEL EQ-004 | Process Engineering / TEL | 3 | 5 | 8 | Contractual recipe transfer clause executed; recipes received
1.3.7 | 3 | Cybersecurity review — Siemens DCS | InfoSec / Engineering | 3 | 5 | 8 | Cybersecurity approval issued for OT network connection
1.3.8 | 3 | Engineering change order management | Engineering | ongoing | 1 | 46 | ECO register maintained throughout program
1.4 | 2 | SUPPLIER FABRICATION & FAT | Supply Chain / Engineering | 26 | 1 | 27 | All equipment at FAT complete; ready to ship
1.4.1 | 3 | EQ-014 (AMAT RTP) — manufacturing & FAT | AMAT / Engineering | 24 | 1 | 25 | RTP units pass FAT; shipping released
1.4.2 | 3 | EQ-002 (Pfeiffer TMP) — manufacturing & FAT [CRITICAL PATH] | Pfeiffer / Engineering | 26 | 1 | 27 | CRITICAL PATH: TMPs pass FAT; shipping released
1.4.3 | 3 | EQ-004 (TEL Batch Furnace) — manufacturing & FAT | TEL / Engineering | 28 | 1 | 29 | Batch furnace FAT complete; JPY invoice settled
1.4.4 | 3 | EQ-003 (Thermco Tube Furnace) — manufacturing & FAT | Thermco / Engineering | 20 | 2 | 22 | Tube furnace FAT at Austin TX; recipe transfer
1.4.5 | 3 | EQ-005 (Brooks SCARA) — manufacturing & FAT | Brooks / Engineering | 14 | 3 | 17 | Robot units FAT complete; MES integration tested
1.4.6 | 3 | EQ-008 (Linde Bulk Gas) — manufacturing | Linde / Facilities | 32 | 1 | 33 | Longest LT: bulk vessel shipped on schedule
1.4.7 | 3 | Remaining equipment — manufacturing & FAT | Various suppliers | 10-18 | 2 | 20 | All units pass FAT; no open NCRs
1.5 | 2 | LOGISTICS | Supply Chain / Logistics | 8 | 15 | 28 | All equipment delivered to site; no customs holds
1.5.1 | 3 | International freight booking — JPY equipment | Logistics | 2 | 15 | 17 | TEL, Daikin, Daifuku freight booked; sea freight
1.5.2 | 3 | International freight booking — EUR equipment | Logistics | 2 | 15 | 17 | EUR equipment freight arranged; road/air options
1.5.3 | 3 | Customs clearance — all international equipment | Trade Compliance | 2 | 17 | 24 | Customs cleared; duty paid; no holds
1.5.4 | 3 | Final delivery & receipt inspection — site | Logistics / Engineering | 3 | 18 | 28 | All equipment received, inspected; CRs raised if needed
1.6 | 2 | SITE READINESS | Facilities / Civil | 20 | 1 | 20 | All utilities ready; floor loading confirmed; permits
1.6.1 | 3 | Structural floor reinforcement — EQ-004 zone | Civil Engineering | 6 | 3 | 9 | Floor certified for 680kg/m² furnace load
1.6.2 | 3 | Electrical infrastructure — transformers & feeds | Electrical Engineering | 10 | 2 | 12 | 480V feeds complete; EQ-011 energized
1.6.3 | 3 | Cooling loop installation — glycol system | Mechanical Engineering | 8 | 4 | 12 | Glycol loop pressure-tested; chiller tie-in complete
1.6.4 | 3 | Gas system infrastructure — hazmat permit | Facilities / Regulatory | 12 | 1 | 13 | Hazmat permit received; gas lines installed
1.6.5 | 3 | Wi-Fi infrastructure upgrade — AMR/OT network | IT/OT Engineering | 6 | 6 | 12 | Wi-Fi survey complete; AP installed; throughput confirmed
1.6.6 | 3 | Clean room / ESD zone preparation | Facilities | 4 | 8 | 12 | ESD flooring installed; HVAC certified; gown area ready
1.7 | 2 | INSTALLATION & COMMISSIONING | Installation / Engineering | 14 | 19 | 33 | All equipment mechanically installed; utilities connected
1.7.1 | 3 | EQ-014 RTP installation | Installation Team | 2 | 20 | 22 | RTP installed; electrical connected; safety interlocks tested
1.7.2 | 3 | EQ-003/004 furnace installation | Installation Team | 3 | 20 | 23 | Furnaces installed; N2 purge connected; crane lift complete
1.7.3 | 3 | EQ-005 robot installation & MES integration | Installation / IT | 3 | 20 | 23 | Robots calibrated; MES endpoints mapped; integration tested
1.7.4 | 3 | EQ-006 overhead conveyor installation | Daifuku / Civil | 4 | 21 | 25 | Track mounts installed; conveyor commissioned; safety scan
1.7.5 | 3 | Utility tie-in — all equipment | Facilities / Engineering | 4 | 22 | 26 | All utilities connected; interlock logic verified
1.7.6 | 3 | EQ-002 TMP installation [CRITICAL PATH] | Installation / Pfeiffer | 2 | 28 | 30 | TMPs installed; roughing pumps connected; leak test
1.7.7 | 3 | EQ-008 bulk gas delivery final installation | Linde / Facilities | 2 | 30 | 32 | Bulk vessel on-site; gas distribution connected; permit closed
1.8 | 2 | PROCESS QUALIFICATION & PRODUCTION RELEASE | Process Engineering | 14 | 33 | 46 | All 15 platforms process-qualified; G5 production release
1.8.1 | 3 | G4 qualification — EQ-014 RTP | Process Eng / AMAT | 3 | 33 | 36 | RTP qualification wafers meet spec; PQ report issued
1.8.2 | 3 | G4 qualification — EQ-003/004 furnaces | Process Eng / Thermco / TEL | 4 | 34 | 38 | Furnace temperature uniformity and oxidation rates certified
1.8.3 | 3 | G4 qualification — EQ-005 robots & MES | Process Eng / Brooks | 3 | 35 | 38 | Robot repeatability ±0.1mm; MES integration validated
1.8.4 | 3 | G4 qualification — all remaining equipment | Process Engineering | 3 | 36 | 39 | All 15 platforms in qualified state
1.8.5 | 3 | SOP documentation & operator training | Process Eng / Training | 3 | 38 | 41 | SOPs issued; all operators trained and signed off
1.8.6 | 3 | Spare parts receipt & inventory loading | Supply Chain / Maintenance | 2 | 38 | 40 | Critical spares stocked; CMMS loaded; reorder triggers set
1.8.7 | 3 | G5 production release — handover to Operations | PM / Process Eng / Ops | 2 | 44 | 46 | Formal handover complete; program closed

## S07_CPM_Master_Schedule
S07 — Critical Path Method (CPM) Master Schedule — Greenfield Expansion Phase II
Activity durations in weeks ¦ Program start: Week 1 = Apr-2025 ¦ Owner: Sourabh Tarodekar ¦ Critical path: EQ-002 Pfeiffer TMP chain = 46 weeks ¦ Total Float = LS − ES = LF − EF ¦ Activities with Float = 0 are on the Critical Path.
Act ID | WBS Ref | Activity Description | Responsible | Duration (wks) | Predecessor(s) | Early Start (ES) | Early Finish (EF) | Late Start (LS) | Late Finish (LF) | Total Float | Critical Path? | Risk Flag | Notes
A01 | 1.1.1 | Program Kick-off & AR Execution | PM / Finance | 1 | — | 1 | 1 | 1 | 1 |  |  | LOW | Start node — AR signed, POs authorized
A02 | 1.2.1 | RFQ Issue — Long-Lead Equipment | Sourcing | 1 | A01 | 2 | 2 | 2 | 2 |  |  | LOW | RFQs to Pfeiffer, TEL, AMAT, Linde
A03 | 1.3.1 | Equipment Technical Spec Review | Process Eng | 2 | A01 | 2 | 3 | 2 | 3 |  |  | LOW | Specs signed off before RFQ response due
A04 | 1.2.2 | Supplier Commercial Evaluation & BAFO | Sourcing | 2 | A02,A03 | 4 | 5 | 4 | 5 |  |  | LOW | Bid tabs; BAFO received from all
A05 | 1.2.7 | FX Forward Contract Execution | Finance | 1 | A04 | 5 | 5 | 5 | 5 |  |  | MOD | EUR+JPY hedges before PO — finance gate
A06 | 1.2.4 | PO Award — EQ-002 Pfeiffer TMP (CRITICAL) | Sourcing | 1 | A04,A05 | 6 | 6 | 6 | 6 |  |  | HIGH | CRITICAL PATH anchor — 26-wk mfg starts here
A07 | 1.2.3 | PO Award — EQ-014 AMAT RTP | Sourcing | 1 | A04,A05 | 6 | 6 | 7 | 7 |  |  | MOD | 1-wk float; 30% deposit = $437.5K at PO
A08 | 1.2.5 | PO Award — EQ-004 TEL Batch Furnace | Sourcing | 1 | A04,A05 | 6 | 6 | 8 | 8 |  |  | MOD | 2-wk float; JPY hedge confirmed
A09 | 1.2.6 | PO Award — All Remaining Equipment | Sourcing | 2 | A04,A05 | 6 | 7 | 6 | 7 |  |  | LOW | EQ-001,003,005,006,007,008,009,010,011,012,013,015
A10 | 1.3.4 | Site Layout & Equipment Placement Freeze | Facilities | 3 | A01 | 2 | 4 | 2 | 4 |  |  | LOW | Civil works blocked until layout approved
A11 | 1.6.4 | Gas System / Hazmat Permit | Facilities/Regulatory | 12 | A10 | 5 | 16 | 5 | 16 |  |  | CRIT | CRITICAL — permit on critical path; submit immediately
A12 | 1.6.2 | Electrical Infrastructure (Transformers) | Electrical Eng | 10 | A10 | 5 | 14 | 5 | 14 |  |  | MOD | 480V feeds; EQ-011 transformer on order wk1
A13 | 1.6.1 | Floor Reinforcement — EQ-004 Zone | Civil Eng | 6 | A10 | 5 | 10 | 5 | 10 |  |  | LOW | Must complete before furnace delivery (Wk 28)
A14 | 1.6.3 | Cooling Loop Installation | Mech Eng | 8 | A12 | 15 | 22 | 15 | 22 |  |  | LOW | Glycol loop after electrical infrastructure
A15 | 1.4.2 | EQ-002 Pfeiffer TMP — Mfg & FAT (CRITICAL) | Pfeiffer | 26 | A06 | 7 | 32 | 7 | 32 |  |  | CRIT | CRITICAL PATH — longest manufacturing chain
A16 | 1.4.1 | EQ-014 AMAT RTP — Mfg & FAT | AMAT | 24 | A07 | 7 | 30 | 8 | 31 |  |  | MOD | 1-wk float; highest-value item
A17 | 1.4.3 | EQ-004 TEL Batch Furnace — Mfg & FAT | TEL | 28 | A08 | 7 | 34 | 9 | 36 |  |  | HIGH | 28-wk mfg; JPY risk; FAT 3 wks
A18 | 1.4.4 | EQ-003 Thermco Tube Furnace — Mfg & FAT | Thermco | 20 | A09 | 8 | 27 | 8 | 27 |  |  | LOW | FAT at Austin TX; recipe transfer
A19 | 1.4.5 | EQ-005 Brooks SCARA — Mfg & FAT | Brooks | 14 | A09 | 8 | 21 | 8 | 21 |  |  | MOD | MES integration tested at FAT
A20 | 1.4.6 | EQ-008 Linde Bulk Gas — Manufacturing | Linde | 32 | A09 | 8 | 39 | 8 | 39 |  |  | MOD | Longest-lead item in remaining equipment
A21 | 1.4.7 | Remaining Equipment — Mfg & FAT | Various | 18 | A09 | 8 | 25 | 8 | 25 |  |  | LOW | EQ-006,007,009,010,011,012,013,015
A22 | 1.5.2 | Freight & Customs — EUR Equipment | Logistics | 3 | A18,A21 | 26 | 28 | 26 | 28 |  |  | LOW | Road/air freight; customs clearance EUR items
A23 | 1.5.1 | Freight & Customs — JPY/EQ-002 (CRITICAL) | Logistics | 3 | A15 | 33 | 35 | 33 | 35 |  |  | MOD | CRITICAL: sea freight after Pfeiffer FAT
A24 | 1.5.1 | Freight & Customs — JPY Other (TEL/Daikin) | Logistics | 3 | A17 | 35 | 37 | 37 | 39 |  |  | MOD | TEL/Daikin/Daifuku sea freight
A25 | 1.7.1 | EQ-014 RTP Installation | Installation | 2 | A16,A12,A14 | 31 | 32 | 32 | 33 |  |  | LOW | RTP installed before furnaces
A26 | 1.7.3 | EQ-005 Robot Install & MES Integration | Installation/IT | 3 | A19,A12 | 22 | 24 | 22 | 24 |  |  | MOD | MES integration — critical dependency
A27 | 1.7.2 | EQ-003/004 Furnace Installation | Installation | 3 | A18,A22,A13 | 29 | 31 | 29 | 31 |  |  | LOW | Crane lift; N2 purge connection
A28 | 1.7.6 | EQ-002 TMP Installation (CRITICAL) | Installation/Pfeiffer | 2 | A23 | 36 | 37 | 36 | 37 |  |  | CRIT | CRITICAL PATH: TMPs installed week 36-37
A29 | 1.7.7 | EQ-008 Bulk Gas Final Installation | Linde/Facilities | 2 | A20,A11 | 40 | 41 | 40 | 41 |  |  | MOD | Permit must be closed; bulk vessel on-site
A30 | 1.7.4 | EQ-006 Daifuku Conveyor Install | Daifuku/Civil | 4 | A24,A12 | 38 | 41 | 38 | 41 |  |  | HIGH | Single-source; civil interface frozen Wk 6
A31 | 1.7.5 | Utility Tie-In — All Equipment | Facilities | 4 | A25,A26,A27,A28 | 38 | 41 | 38 | 41 |  |  | LOW | All utilities connected; interlock test
A32 | 1.3.2 | FAT Protocol Development | Process Eng | 3 | A03 | 4 | 6 | 4 | 6 |  |  | LOW | FAT protocols issued to all suppliers
A33 | 1.3.5 | MES/SCADA/DCS Integration Spec | Controls/IT | 4 | A03 | 4 | 7 | 4 | 7 |  |  | MOD | Integration spec required before FAT testing
A34 | 1.8.1 | G4 Qualification — EQ-014 RTP | Process Eng | 3 | A25,A31 | 42 | 44 | 42 | 44 |  |  | LOW | First tool qualified
A35 | 1.8.2 | G4 Qualification — Furnaces | Process Eng | 4 | A27,A31 | 42 | 45 | 42 | 45 |  |  | MOD | Temperature uniformity certification
A36 | 1.8.3 | G4 Qualification — Robots & MES | Process Eng | 3 | A26,A31 | 42 | 44 | 42 | 44 |  |  | MOD | Robot repeatability + MES validation
A37 | 1.8.4 | G4 Qualification — All Remaining | Process Eng | 3 | A28,A29,A30,A31 | 42 | 44 | 42 | 44 |  |  | LOW | All 15 platforms qualified
A38 | 1.8.5 | SOP Documentation & Operator Training | Training/Ops | 3 | A34,A35,A36,A37 | 45 | 47 | 44 | 46 |  |  | LOW | SOPs issued; all operators certified
A39 | 1.8.7 | G5 Production Release — Program Close | PM/Ops | 2 | A38 | 46 | 47 | 46 | 47 |  |  | LOW | Formal handover; program closed
CRITICAL PATH SUMMARY
Total program duration (critical path, weeks)
Number of critical path activities (Float = 0)
Critical path sequence | A01 → A06 → A15 → A23 → A28 → A31 → A34/35/36/37 → A38 → A39
Longest chain | EQ-002 Pfeiffer TMP: PO → 26-wk mfg → FAT → freight → install → PQ; spans Weeks 6-44
Key schedule risk | A11 Gas System / Hazmat Permit — 12-week permit must start Week 5; any delay blocks gas system install
Key commercial risk | A06 EQ-002 Pfeiffer PO — single-source; no float; 30-day PO delay = 30-day program delay

## S08_Program_Milestone_Roadmap
S08 — Program Milestone Roadmap — Greenfield Expansion Phase II
Phase-gate roadmap from AR approval to production release ¦ Owner: Sourabh Tarodekar ¦ All dates Apr-Dec 2025 ¦ Gates: G0 (Concept) -> G5 (Production Release)
PROGRAM GATES
Gate | Month | Status Label
G0+G1 | Apr-25 | Approved
G2 | Aug-25 | FAT Complete
G3 | Oct-25 | Install
G4 | Nov-25 | PQ Start
G5 | Dec-25 | Production Release
KEY PROGRAM MILESTONES
# | Milestone | Gate | Target Date | Status | Owner | Notes
M01 | AR Approved — Phase II | G0/G1 | 2025-04-07 | APPROVED | Sourabh Tarodekar | Long-lead PO authority granted; cost centre CC-4421 open
M02 | All Long-Lead POs Placed | G1 | 2025-04-28 | COMPLETE | Sourcing | EQ-002,004,008,014 POs placed; FX hedges executed
M03 | Site Layout Frozen | — | 2025-04-14 | APPROVED | Facilities | Civil works can proceed; no further layout changes
M04 | Hazmat Permit Submitted | — | 2025-04-14 | IN PROGRESS | Regulatory | Permit application filed; 12-wk processing time
M05 | All Equipment POs Placed | G1 | 2025-05-12 | COMPLETE | Sourcing | Full PO portfolio placed; supplier schedule confirmed
M06 | Site Utilities Complete (Elec + Cool) | — | 2025-08-11 | ON TRACK | Facilities | Electrical feeds + glycol loop ready before delivery
M07 | Hazmat Permit Received | — | 2025-07-07 | ON TRACK | Regulatory | CRITICAL — blocks gas system install if delayed
M08 | EQ-014 AMAT RTP FAT Complete | G2 | 2025-09-22 | ON TRACK | Engineering | First FAT complete; highest-value item
M09 | EQ-002 Pfeiffer TMP FAT Complete | G2 | 2025-10-20 | CRITICAL PATH | Engineering / Pfeiffer | CRITICAL PATH — no float; monitor weekly
M10 | All Equipment Delivered to Site | G3 | 2025-10-27 | ON TRACK | Logistics | All 15 platforms on-site; receipt inspection complete
M11 | All Equipment Installed | G3 | 2025-11-10 | ON TRACK | Installation | Mechanical install + utility tie-in complete
M12 | G4 Process Qualification Start | G4 | 2025-11-10 | PLANNED | Process Eng | PQ begins; first tools: EQ-014 RTP, EQ-003 Furnace
M13 | Full Process Qualification Complete | G4 | 2025-12-01 | PLANNED | Process Eng | All 15 platforms in qualified state; PQ reports issued
M14 | Operator Training Complete | — | 2025-12-08 | PLANNED | Training / Ops | All operators trained + certified on SOPs
M15 | G5 Production Release | G5 | 2025-12-22 | PLANNED | Sourabh Tarodekar | Formal handover to Operations; program closed

## S09_Deployment_Timeline
S09 — Equipment Deployment Timeline & Critical Path Model — CapEx Phase II Program
All durations in weeks ¦ Program Start: Week 1 (2025-Q2) ¦ Critical Path items highlighted in RED ¦ Inputs in BLUE ¦ [MFG] Mfg [FAT] Factory Accept. Test [SHP] Shipping [INS] Installation [UTL] Utility Hookup [PQ] Process Qual
Equipment ID | Equipment / Tool | Supplier | Mfg (wks) | FAT (wks) | Shipping (wks) | Installation (wks) | Utility Hookup (wks) | Process Qual (wks) | Total Deploy Duration (wks) | Program Start Week | Delivery/Install Compl. (Wk#) | PQ Complete (Wk#) | Critical Path? | Float (wks) | Risk Flag | Predecessor Dependency | Engineering Notes
EQ-014 | RTP – Applied Materials (CRITICAL PATH) | AMAT | 24 | 2 | 3 | 4 | 2 | 6 |  | 1 |  |  | YES |  | HIGH | None — first install | Highest-value item; finance AR approval gate at Week 2; 30% deposit required; longest total duration
EQ-004 | Batch Oxidation Furnace | TEL | 28 | 2 | 3 | 4 | 2 | 5 |  | 1 |  |  | YES |  | HIGH | EQ-013 (pump) must install first | JPY FX exposure; overseas FAT at TEL Japan; import clearance estimated 1 week
EQ-003 | Tube Furnace System | Thermco | 20 | 2 | 3 | 4 | 2 | 5 |  | 2 |  |  | YES |  | MODERATE | EQ-013 (pump) must install first | Parallel install path with EQ-004 possible; process recipe transfer at FAT
EQ-006 | Overhead Track Conveyor | Daifuku | 30 | 2 | 3 | 5 | 2 | 0 |  | 1 |  |  | YES |  | HIGH | Civil mounts must be complete (Week 8) | Civil interface drawings required 8 wks before delivery; structural review required
EQ-002 | Turbomolecular Pump | Pfeiffer | 26 | 2 | 3 | 3 | 1 | 0 |  | 1 |  |  | YES |  | CRITICAL | EQ-003, EQ-004 dependent | SINGLE SOURCE – CRITICAL RISK; no qualified alt; escalated to VP; daily status
EQ-008 | Bulk Gas Storage | Linde | 32 | 2 | 3 | 5 | 3 | 0 |  | 1 |  |  | YES |  | HIGH | EQ-007 (gas cabinet) install after | Longest lead time in portfolio (32 wks mfg); PO must be placed Week 1; civil pad parallel
EQ-001 | Dry Screw Vacuum Pump | Edwards | 18 | 2 | 3 | 3 | 1 | 0 |  | 2 |  |  | No |  | MODERATE | EQ-003 dependent | Alt vendor (Busch) available; paired install with EQ-013; N2 purge line required
EQ-013 | Roots Blower Booster | Busch | 15 | 2 | 3 | 3 | 1 | 0 |  | 2 |  |  | No |  | LOW | EQ-001 must install first | Paired with EQ-001; coordinated delivery schedule; low supply risk
EQ-007 | Gas Cabinet | Air Liquide | 22 | 2 | 3 | 4 | 2 | 0 |  | 2 |  |  | No |  | MODERATE | EQ-008 (bulk gas) commissioned first | Hazmat permit on critical path; permit application must be filed immediately
EQ-005 | SCARA Robot (x6) | Brooks | 14 | 2 | 3 | 4 | 1 | 0 |  | 3 |  |  | No |  | MODERATE | EQ-006 (conveyor) operational first | MES integration requires 4 wks; SW engineer on-site for FAT and site install
EQ-009 | DCS – Siemens S7-1500 (x5) | — | 14 | 2 | 3 | 3 | 1 | 0 |  | 2 |  |  | No |  | LOW | None — independent | Cybersecurity review adds 3 wks; submit InfoSec package 6 wks pre-install
EQ-010 | SCADA Platform | Inductive Automation | 0 | 2 | 0 | 2 | 1 | 0 |  | 4 |  |  | No |  | LOW | EQ-009 DCS must be installed | Software license; no physical shipping; IT infrastructure and server required on-site first
EQ-011 | Dry-Type Transformer | ABB | 20 | 2 | 3 | 3 | 2 | 0 |  | 1 |  |  | No |  | MODERATE | None — utility infrastructure | Partial reuse from legacy program; refurbishment scope adds 2 wks to schedule
EQ-012 | Process Chiller (x3) | Daikin | 20 | 2 | 3 | 4 | 2 | 0 |  | 2 |  |  | No |  | MODERATE | EQ-011 (transformer) must be live | Glycol loop design must be finalized by Week 6; coordinate with mechanical engineering
EQ-015 | AMR Fleet (x10) | MiR | 18 | 2 | 3 | 3 | 1 | 0 |  | 5 |  |  | No |  | LOW | EQ-006 (conveyor) track complete | Wi-Fi infrastructure upgrade required 6 wks before delivery; IT lead time on critical path
PROGRAM SCHEDULE SUMMARY
Earliest Equipment Delivery (Week #)
Latest PQ Completion (Week #)
Critical Path Duration (Program End, weeks)
Total Equipment Platforms
Critical Path Items
HIGH or CRITICAL Risk Items
Avg Total Deployment Duration (wks)
Items with Zero Float (No Schedule Flexibility)

## S10_Capacity_Planning
S10 — Capacity Planning Model — Annual Production Capacity Supported by Equipment Portfolio
Inputs from S02_Equipment_Portfolio and S01_Disclaimer_Assumptions ¦ Identifies bottlenecks ¦ Models +20% demand surge scenario
CAPACITY MODEL PARAMETERS
Parameter | Value | Unit | Source
Equipment Uptime (%) |  |  | S01 — 92% target
Planned Maint Downtime (%) |  |  | S01 — 4% allocated
Effective Uptime (%) |  |  | Uptime minus Planned Maint (formula)
Process Yield (%) |  |  | S01 — 96% yield
Baseline Demand (units/yr) | 750000 |  | Engineering baseline — current program requirement
Surge Scenario (+20%) Demand (units/yr) |  |  | Stress test: 20% volume increase
EQUIPMENT CAPACITY MODEL — BASELINE vs SURGE SCENARIO
Equipment ID | Equipment Category | Tool Type | Throughput (units/hr) | Quantity | Op Hours/Year | Effective Uptime (%) | Annual Capacity (units/yr) | Baseline Demand (units/yr) | Capacity Cushion (units) | Tool Contribution to Portfolio Cap (%) | Surge Demand (+20%, units/yr) | Surge Contribution (%) | Bottleneck Flag
EQ-001 | Vacuum Pump System | Dry Screw Vacuum Pump | N/A | 4 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-002 | Vacuum Pump System | Turbomolecular Pump Assembly | N/A | 3 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-003 | High-Temp Furnace | Tube Furnace System – 8-zone | 24 | 2 | 8320 | [7 empty] | ⚠ BOTTLENECK (portfolio-level surge >72% utilization)
EQ-004 | High-Temp Furnace | Batch Oxidation Furnace | 18 | 2 | 8320 | [7 empty] | ⚠ BOTTLENECK (portfolio-level surge >72% utilization)
EQ-005 | Robotics / Automation | SCARA Wafer Transfer Robot | N/A | 6 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-006 | Robotics / Automation | Overhead Track Conveyor | N/A | 1 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-007 | Gas Handling System | Process Gas Cabinet | N/A | 4 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-009 | PLC Control System | DCS – Siemens S7-1500 | N/A | 5 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-011 | Facility Infra | Dry-Type Transformer | N/A | 2 | 8760 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-012 | Facility Infra – Cooling | Process Chiller System | N/A | 3 | 8760 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-013 | Vacuum Pump System | Roots Blower Booster | N/A | 6 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
EQ-014 | High-Temp Furnace | RTP – Rapid Thermal Processor | 32 | 2 | 8320 | [7 empty] | ⚠ BOTTLENECK (portfolio-level surge >72% utilization)
EQ-015 | Robotics / Automation | AMR Fleet (x10) | N/A | 1 | 8320 |  | — | — | — | — | — | — | SUPPORT EQUIPMENT
CAPACITY SUMMARY & BOTTLENECK ANALYSIS
Total Annual Capacity (Process Tools Only)
Baseline Demand
Baseline Capacity Cushion
Baseline Utilization
Surge Demand (+20%)
Bottleneck Equipment (Surge) | Batch Oxidation Furnace (EQ-004) — lowest individual Annual Capacity among process tools
Max Surge Utilization

## S11_Demand_Forecast
S11 — Demand Forecast Model — Advanced Manufacturing Program (2023-2025)
Time-series demand forecast by product family ¦ Owner: Sourabh Tarodekar ¦ Feeds S10_Capacity_Planning (baseline demand input) ¦ Forecast accuracy tracked quarterly
FORECAST ASSUMPTIONS
Baseline Annual Demand (2025 program target) | 750000
Surge Scenario (+20%) | 900000
Downside Scenario (-20%) | 600000
Committed Customer Volume (Phase II driver, incremental) | 312000
QUARTERLY FORECAST vs ACTUALS — 2023 THROUGH 2025
Period | Baseline Forecast | Upside (+20%) | Downside (-20%) | Actual/Committed | Forecast Accuracy (%) | Rolling 3-Qtr Avg | Variance vs Fcst | Status | Forecast Source | Notes
Q1-2023 | 520000 |  |  | 505000 |  | TBC |  | ACTUAL | S&OP Review | Production ramp; new process tools qualified Q1
Q2-2023 | 540000 |  |  | 528000 |  | TBC |  | ACTUAL | S&OP Review | Slight volume shortfall; MES integration delay
Q3-2023 | 565000 |  |  | 571000 |  |  |  | ACTUAL | S&OP Review | On track; customer pull-in request +6K units
Q4-2023 | 575000 |  |  | 567000 |  |  |  | ACTUAL | S&OP Review | Seasonal demand pattern confirmed
Q1-2024 | 590000 |  |  | 580000 |  |  |  | ACTUAL | S&OP Review | Q1 softness as expected; customer forecast revised
Q2-2024 | 610000 |  |  | 624000 |  |  |  | ACTUAL | S&OP Review | Strong pull; customer volume commitment +35K
Q3-2024 | 630000 |  |  | 618000 |  |  |  | ACTUAL | S&OP Review | Slight miss due to competitor product shift
Q4-2024 | 650000 |  |  | 661000 |  |  |  | ACTUAL | S&OP Review | Year-end strong; customer forecast upgrade for 2025 Phase II program
Q1-2025 | 680000 |  |  | 675000 |  |  |  | ACTUAL | S&OP Review | Phase II program approved; capacity expansion underway
Q2-2025 | 710000 |  |  | 718000 |  |  |  | ACTUAL | S&OP Review | All POs placed; equipment in fabrication
Q3-2025 | 735000 |  |  | TBC | TBC |  | TBC | FORECAST | S&OP Review | Forecast confirmed; delivery/install on schedule
Q4-2025 | 750000 |  |  | TBC | TBC |  | TBC | FORECAST | S&OP Review | TARGET: G5 production release; full capacity online
DEMAND BY PRODUCT FAMILY — 2025 ANNUAL FORECAST
Product Family | Description | 2023 Actual | 2024 Actual | Q1-2025 | Q2-2025 | Q3-2025 | Q4-2025 | 2025 Forecast | CAGR 2023->25 | Required Capacity (u/hr) | Constrained by Equip | Priority
PF-A | Advanced Process Products (High-Temp Furnace) | 210000 | 260000 | 70000 | 73000 | 78000 | 79000 |  |  |  | EQ-003/004 | 1
PF-B | Precision Robotics Assembly | 150000 | 190000 | 54000 | 56000 | 58000 | 57000 |  |  |  | EQ-005 | 2
PF-C | Gas-Phase Deposition (RTP Products) | 115000 | 142000 | 36000 | 37000 | 38000 | 39000 |  |  |  | EQ-014 | 3
PF-D | Infrastructure / Support Builds | 75000 | 58000 | 18000 | 18500 | 19000 | 19500 |  |  |  | EQ-009/010 | 4
TOTAL | All Product Families

## S12_AR_Summary
S12 — Capital Appropriations Request (AR) Summary — Greenfield Expansion Phase II
Prepared by: Sourabh Tarodekar, Program Manager ¦ Submitted to: VP Engineering & CFO ¦ Date: 2025-Q1 ¦ AR Number: AR-2025-0082
PROGRAM INFORMATION
Program Name | Greenfield Expansion Phase II — Advanced Manufacturing Facility | Business Unit | Semiconductor & Advanced Process Division
Program Manager | Sourabh Tarodekar | Finance Partner | R. Patel
AR Reference | AR-2025-0082 | Revision | Rev 1.0 — Initial Submission
Submission Date | 2025-03-19 | Required Approval By | 2025-04-07 (Week 4 — Long-lead PO gate)
Program Start | 2025-Q2 (Week 1) | Program End | 2025-Q4 (Week 47 — PQ Complete)
Approval Authority | VP Engineering + CFO (>$10M threshold) | Cost Centre | CC-4421 — Manufacturing Capital Projects
BUSINESS CASE SUMMARY
This appropriations request funds the capital equipment procurement, installation, and qualification of 15 equipment platforms required to establish a new advanced manufacturing process line within the Greenfield Expansion Phase II facility. The program supports a committed customer volume increase of 35% beginning 2025-Q4, requiring new process capacity that cannot be delivered by existing installed equipment. The recommended investment (Scenario B — Baseline Program) delivers 312,000 units/year annual capacity at 92% uptime, with a 10-year NPV of $9.5M over the minimum-CapEx alternative. The program is expected to achieve first production output by Week 47 (2025-Q4).
CAPITAL BUDGET SUMMARY
Cost Category | Equipment Count | Unit Cost Range (USD) | Total Equipment Cost (USD) | Installation Cost (USD) | Total Line Item (USD) | % of Total CapEx
Vacuum Pump Systems | 3 | $125K-$310K | 2420000 | 256000
High-Temperature Furnaces | 3 | $520K-$875K | 4150000 | 314000
Robotics & Automation | 3 | $275K-$420K | 2450000 | 238000
Gas Handling Systems | 2 | $195K-$340K | 1120000 | 248000
PLC / Control Systems | 2 | $85K-$165K | 1080000 | 99000
Facility Infrastructure | 2 | $210K-$295K | 1305000 | 190000
SUBTOTAL — Equipment + Installation | [5 empty] | 100%
Contingency Reserve (10% of CapEx)
FX Hedge Reserve (EUR + JPY exposure) |  |  |  |  | 485000
Engineering NRE & Program Management |  |  |  |  | 320000
TOTAL APPROPRIATIONS REQUEST (USD)
Budget Reconciliation Note: Equipment and installation totals above are derived directly from S02_Equipment_Portfolio (Equipment Purchase Total, Installation Total, Combined CapEx). Scenario Analysis (S13) Scenario B budget of $40.04M represents a broader multi-phase strategic program comparison with different cost assumptions and is not directly comparable to this Phase II AR.
FINANCIAL JUSTIFICATION & RETURN METRICS
Metric | Value | Unit | Basis / Source
10-Year NPV of Investment (vs Min-CapEx alternative) | 9520000 | $ | Linked to S13 Scenario B vs A NPV calculation
Estimated IRR | 14.2% | % | Based on incremental OpEx savings over 10 years at 8% WACC
Simple Payback Period | 4.2 | yrs | Payback of incremental CapEx vs Scenario A through OpEx savings
Annual Production Capacity Enabled | 312000 | units | At 92% uptime; S10 Capacity Planning model
Annual OpEx Savings vs Scenario A | 1390000 | $/yr | Energy + maintenance + downtime reduction
Equipment Depreciation Method | MACRS 7-yr | — | Per Finance / Tax Counsel guidance
After-Tax IRR (21% effective rate) | 11.2% | % | Estimated; Finance to confirm in detailed model
Revenue Enabled (at $145/unit avg selling price) | 45240000 | $/yr | Based on 312K units x $145 ASP
KEY RISKS & MITIGATIONS (SUMMARY FOR APPROVERS)
Risk | Impact | Probability | Mitigation | Residual Risk
EQ-002 Pfeiffer single-source — no qualified alt supplier | Schedule delay 4-8 wks if pump fails or delivery slips | MODERATE | Safety stock of 2 units; alt vendor qual in parallel (Shimadzu) | LOW-MODERATE
EQ-007 hazmat permit lead time exceeds program schedule | Gas system install delayed 2+ wks — blocks furnace PQ | MODERATE | Expedited permit via regulatory consultant; contingency bottle gas supply | LOW
JPY/EUR FX adverse movement (>5%) | Up to $285K budget overrun on EUR/JPY equipment | LOW | Forward FX contracts executed; FX reserve in AR | LOW
EQ-004 structural floor reinforcement scope growth | Additional $30-50K if reinforcement scope expands | LOW | Structural engineer engaged; early assessment complete | VERY LOW
Customer demand shortfall vs forecast | Reduced ROI; excess capacity created | LOW | Program phased — Phase III expansion deferred if demand misses | LOW
EXECUTIVE RECOMMENDATION
RECOMMENDATION: APPROVE — Scenario B Baseline Program ($40.04M total budget)
The investment delivers a 14.2% IRR against an 8.0% hurdle rate, a 4.2-year payback, and $9.5M NPV over 10 years vs the minimum-CapEx alternative. Revenue enabled of $45.2M/yr supports the committed customer volume increase of 35% from 2025-Q4. All financial metrics exceed approval thresholds.

## S13_Scenario_Analysis
S13 — Scenario Analysis — CapEx Program Investment Decision Framework
Compares three capital investment scenarios across NPV, TCO, capacity, supply chain risk, and schedule ¦ Scenario A = Minimum CapEx (Low Upfront / Higher OpEx) ¦ Scenario B = Baseline Program (Balanced) ¦ Scenario C = Premium Build (High CapEx / Lowest OpEx)
CAPITAL EXPENDITURE (CAPEX)
Parameter | Units | Scenario A | Scenario B | Scenario C | B vs A Delta | C vs B Delta | Best Scenario | Notes
Total Equipment Purchase Cost | $ | 24500000 | 32800000 | 38500000 |  |  | Scenario B | Scenario A uses domestic/value suppliers; C uses premium OEM across all platforms
Total Installation Cost | $ | 2800000 | 3600000 | 4200000 |  |  | Scenario A | Installation costs scale with equipment complexity and supplier requirements
Total CapEx (Equipment + Install) | $ | 27300000 | 36400000 | 42700000 |  |  | Scenario A | Formula: Purchase + Install; Scenario A ~33% lower CapEx than C
Contingency Reserve (10% of CapEx) | $ | 2730000 | 3640000 | 4270000 |  |  | Scenario A | Standard 10% contingency; Scenario C highest absolute contingency
Total Program Budget (incl. contingency) | $ | 30030000 | 40040000 | 46970000 |  |  | Scenario A | Total appropriations request basis for each scenario
OPERATING EXPENDITURE (OPEX — ANNUAL)
Parameter | Units | Scenario A | Scenario B | Scenario C | B vs A Delta | C vs B Delta | Best Scenario | Notes
Annual Energy Cost (all equipment) | $/yr | 1850000 | 1620000 | 1380000 |  |  | Scenario C | Scenario A older/less efficient equipment; Scenario C latest-gen low-energy platforms
Annual Maintenance Cost | $/yr | 1960000 | 1475000 | 1225000 |  |  | Scenario C | Scenario A value-tier has higher failure rate and maint burden
Annual Spare Parts Cost | $/yr | 520000 | 385000 | 295000 |  |  | Scenario C | Premium OEM (Scenario C) has longer MTBF; fewer spare parts events
Annual Downtime Cost (MTBF/MTTR model) | $/yr | 1260000 | 720000 | 396000 |  |  | Scenario C | MTBF-based: Sc A avg MTBF 2,400hr; Sc B 3,500hr; Sc C 5,200hr
Total Annual OpEx | $/yr | 5590000 | 4200000 | 3296000 |  |  | Scenario C | Formula: Sum of above OpEx lines; C saves $2.3M/yr vs A
FINANCIAL MODEL (10-YEAR HORIZON)
Parameter | Units | Scenario A | Scenario B | Scenario C | B vs A Delta | C vs B Delta | Best Scenario | Notes
10-Year Cumulative OpEx | $ | 55900000 | 42000000 | 32960000 |  |  | Scenario C | Escalated at 2.5%/yr inflation; C significantly lower over 10-yr horizon
NPV of OpEx Savings vs Scenario A | $ | 0 | 9520000 | 14630000 |  |  | Scenario C | NPV at 8% discount rate; Scenario C generates $14.6M NPV savings vs A
Estimated IRR | % | N/A | 14.2% | 18.7% | N/A |  | Scenario C | IRR on incremental investment relative to Scenario A baseline
Simple Payback vs Scenario A (yrs) | yrs | N/A | 4 | 4 | N/A |  | Scenario C | Payback of incremental CapEx premium through OpEx savings
CAPACITY & PERFORMANCE
Parameter | Units | Scenario A | Scenario B | Scenario C | B vs A Delta | C vs B Delta | Best Scenario | Notes
Annual Production Capacity (units/yr) | units | 228000 | 312000 | 368000 |  |  | Scenario C | Scenario C premium equipment delivers highest throughput and uptime
Equipment Uptime (%) | % | 88% | 92% | 95.5% |  |  | Scenario C | Scenario A value-tier has higher unplanned downtime; C has best SLA terms
Process Yield (%) | % | 93.5% | 96% | 97.5% |  |  | Scenario C | Process yield linked to equipment precision and repeatability spec
SUPPLY CHAIN RISK
Parameter | Units | Scenario A | Scenario B | Scenario C | B vs A Delta | C vs B Delta | Best Scenario | Notes
Single-Source Components | count | 8 | 5 | 3 |  |  | Scenario C | Scenario A relies on more sole-source suppliers due to cost-driven selection
Avg Supplier Lead Time (wks) | wks | 23.4 | 19.8 | 17.2 |  |  | Scenario C | Premium suppliers (Scenario C) have better supply chain infrastructure
Supply Chain Risk Index (composite) | score | 38.5 | 24.2 | 16.8 |  |  | Scenario C | Composite index; lower = lower risk
SCHEDULE & DEPLOYMENT
Parameter | Units | Scenario A | Scenario B | Scenario C | B vs A Delta | C vs B Delta | Best Scenario | Notes
Critical Path Duration (weeks) | wks | 46 | 42 | 38 |  |  | Scenario C | Scenario C suppliers have shorter manufacturing lead times and dedicated PM support
Program End Date (Week # from start) | wks | 52 | 47 | 43 |  |  | Scenario C | Earlier qualification in Scenario C allows faster ramp to production revenue
Schedule Risk Items | count | 7 | 5 | 3 |  |  | Scenario C | Fewer risk items in Scenario C; better supplier program management
WEIGHTED DECISION SCORECARD & PROGRAM RECOMMENDATION
Dimension | Weight | Score A (1-5) | Score B (1-5) | Score C (1-5) | Wtd Score A | Wtd Score B | Wtd Score C | Winner
Capital Cost (Lower = Better) | 20% | 5 | 3 | 2 |  |  |  | A
10-Yr Total Cost of Ownership | 20% | 2 | 4 | 5 |  |  |  | C
Financial Return (NPV/IRR) | 15% | 1 | 4 | 5 |  |  |  | C
Production Capacity | 10% | 2 | 4 | 5 |  |  |  | C
Supply Chain Risk | 15% | 2 | 4 | 5 |  |  |  | C
Schedule & Deployment Risk | 10% | 2 | 4 | 5 |  |  |  | C
Operational Reliability / Uptime | 10% | 2 | 4 | 5 |  |  |  | C
TOTAL WEIGHTED SCORE
PROGRAM RECOMMENDATION
RECOMMENDED SCENARIO: SCENARIO B — Baseline Program (APPROVED)
Scenario B delivers 312,000 units/yr capacity, 14.2% IRR, and $9.5M NPV over 10 years vs Scenario A. While Scenario C scores marginally higher on the weighted scorecard, it was not selected because the $47M total budget exceeds the divisional CapEx approval ceiling for a single program phase. Scenario B provides the optimal balance of financial return, risk profile, and capital efficiency within approved limits. Total budget $40.04M is within the $42M divisional CapEx approval ceiling; 14.2% IRR exceeds the 8% hurdle rate with a 4.2-year payback; 312,000 units/yr capacity supports the committed 35% customer volume increase. AR-2025-0082 was submitted and approved on this basis.

## S14_CashFlow_Model
S14 — CapEx Cash Flow Model — Monthly Detail & Quarterly Summary (2025 Program)
Program: Greenfield Expansion Phase II ¦ Owner: Sourabh Tarodekar ¦ Merged monthly/quarterly model — quarterly totals derived from monthly rows (SUMIF). Payment terms: 25% Deposit / 40% Milestone / 35% Delivery.
PAYMENT & PROGRAM ASSUMPTIONS
Deposit % at PO Placement | 25%
Manufacturing Milestone % | 40%
Delivery Payment % | 35%
Total AR Budget
MONTHLY SPEND PROFILE — Apr 2025 through Dec 2025
# | Month | Equip. Purchases (USD) | Install & Commissioning (USD) | Facility Infra & FX Reserve (USD) | NRE/Engineering (USD) | Total Period Spend (USD) | Cumulative Spend (USD) | % of AR Budget | Quarter | Planned Milestone | Notes
1 | Apr-25 | 3312500 | 0 | 512000 | 122500 |  |  |  | Q2-2025 | G1: AR approved; long-lead POs placed | Deposits: EQ-001/2/3/5/9/11/13/14/15; hazmat permit submitted
2 | May-25 | 412500 | 0 | 431000 | 97500 |  |  |  | Q2-2025 | EQ-004/006/012 deposits; civil works begin | TEL furnace + Daifuku conveyor + Daikin chiller deposits
3 | Jun-25 | 660000 | 78000 | 283000 | 95000 |  |  |  | Q2-2025 | EQ-005 milestone; robot FAT prep | Brooks SCARA manufacturing milestone payment
4 | Jul-25 | 948000 | 138000 | 227000 | 90000 |  |  |  | Q3-2025 | EQ-001/009/013 milestones; electrical infra | Pump + DCS milestones; electrical feeds energized
5 | Aug-25 | 1168000 | 207000 | 252000 | 85000 |  |  |  | Q3-2025 | EQ-003/011 milestones; cooling loop | Thermco furnace + ABB transformer manufacturing milestone
6 | Sep-25 | 700000 | 258000 | 305000 | 80000 |  |  |  | Q3-2025 | EQ-007/015 milestones; hazmat permit rcvd | Air Liquide gas + MiR AMR milestones; permit closes
7 | Oct-25 | 912500 | 323000 | 250000 | 75000 |  |  |  | Q4-2025 | EQ-014 milestone; deliveries begin | AMAT RTP manufacturing milestone; EUR equipment deliveries
8 | Nov-25 | 577500 | 353000 | 230000 | 70000 |  |  |  | Q4-2025 | EQ-001/009/013 deliveries; installation peak | Pump sets + DCS delivered; mechanical installation begins
9 | Dec-25 | 637000 | 405000 | 60000 | 65000 |  |  |  | Q4-2025 | G3/G4: final deliveries; PQ begins | Thermco + Air Liquide + Daikin + MiR delivered; PQ start
TOTAL 2025
QUARTERLY CASH FLOW SUMMARY — DERIVED FROM MONTHLY DETAIL
Quarter | Equip. Purchases | Install & Commissioning | Facility Infra & FX Reserve | NRE/Engineering | Total Quarter Spend | Cumul. Spend | % of AR Budget
Q2-2025
Q3-2025
Q4-2025
PROGRAM TOTAL

## S15_FX_Exposure_Model
S15 — FX Exposure & Currency Risk Model — EUR / JPY Equipment Purchases
Program: Greenfield Expansion Phase II ¦ ~40% of portfolio denominated in EUR or JPY ¦ All baseline/stress rates from S01_Disclaimer_Assumptions ¦ Hedge status linked to cash flow schedule
FX RATE ASSUMPTIONS (Linked from S01_Disclaimer_Assumptions)
Rate Parameter | Baseline | Adverse | Favorable | Notes
USD/EUR (baseline, USD per EUR) |  |  |  | 1% move in EUR/USD ~ $85K portfolio impact
USD/JPY (baseline, JPY per USD) |  |  |  | Stronger JPY (lower rate) = higher USD cost
EQUIPMENT-LEVEL FX EXPOSURE ANALYSIS
Equip ID | Tool Description | Ccy | Contract Value (Local Ccy) | Baseline FX Rate | Baseline USD Cost | Adverse FX Rate | Adverse USD Cost | Adverse Impact (USD) | Favorable FX Rate | Favorable USD Cost | Hedge Status | Hedge Rate | Notes
EQ-001 | Dry Screw Vacuum Pump (x4) | EUR | [8 empty] | HEDGED | 1.085 | Forward contract executed; rate locked at 1.085 through Q3-2025
EQ-002 | Turbomolecular Pump (x3) | EUR | [8 empty] | HEDGED | 1.09 | Forward contract at baseline rate; expires Q3-2025
EQ-004 | Batch Oxidation Furnace — TEL (x2) | JPY | [8 empty] | HEDGED | 149 | Forward contract at 149.0 JPY/USD; DEC-003 + CR-008 reference
EQ-006 | Overhead Conveyor — Daifuku | JPY | [8 empty] | HEDGED | 149 | Hedged as part of JPY program-wide forward contract
EQ-007 | Gas Handling Cabinet (x4) | EUR | [8 empty] | OPEN | N/A | Quote under negotiation; PO not yet placed; unhedged exposure
EQ-008 | Bulk Gas Storage — Linde | EUR | [8 empty] | HEDGED | 1.09 | Hedged at PO placement; long-lead item requires early hedge
EQ-009 | DCS — Siemens S7-1500 (x5) | EUR | [8 empty] | HEDGED | 1.09 | Hedged with EUR program forward; expires Q2-2025
EQ-012 | Process Chiller — Daikin (x3) | JPY | [8 empty] | HEDGED | 149 | Included in JPY hedge package; Daikin invoice in JPY
EQ-013 | Roots Blower Booster (x6) | EUR | [8 empty] | HEDGED | 1.085 | Forward at 1.085; coordinated with EQ-001 Edwards delivery schedule
EQ-015 | AMR Fleet — MiR (x10) | EUR | [8 empty] | HEDGED | 1.09 | Hedged at PO placement; forward expires Q3-2025
FX PORTFOLIO TOTALS
FX EXPOSURE SUMMARY & HEDGE EFFECTIVENESS
Total EUR-Denominated Spend (baseline USD)
Total JPY-Denominated Spend (baseline USD)
Total Portfolio FX-Exposed Spend (baseline USD)
Adverse FX Impact (if fully unhedged)
Items Fully Hedged
Items with Open Unhedged Exposure
FX Reserve in AR Budget (USD) | 485000
Net FX Risk After Reserve

## S16_Supply_Chain_Risk
S16 — Supply Chain Risk & Lead-Time Analysis — CapEx Equipment Program
Risk Score = Delay Probability x Schedule Impact Score x Replacement Difficulty ¦ Heatmap tiers: LOW / MODERATE / HIGH / CRITICAL ¦ Single-source components auto-flagged CRITICAL if Risk Score > 20 ¦ Program ID column enables portfolio-wide rollups
Equip Ref | Supplier | Component / Sub-System | Std Lead (wks) | Current Lead (wks) | Delay Prob. (0-1) | Sched. Impact (1-5) | Replace Difficulty (1-5) | Composite Risk Score | Risk Tier | Single Source? | Buffer Stock? | Mitigation Action | Status | Program ID
EQ-001 | Edwards Vacuum | Dry Screw Pump – Complete Unit | 14 | 18 | 35% | 3 | 2 |  |  | No | No | Expedite order; confirm delivery schedule with supplier weekly; pre-qualify Busch as alt | IN PROGRESS | PRG-001
EQ-002 | Pfeiffer Vacuum | Turbomolecular Pump – Complete Unit | 16 | 26 | 55% | 5 | 5 |  |  | YES | No | CRITICAL PATH: Escalate to VP Supply Chain; evaluate rebuilt unit as bridge; initiate alt vendor qual | ESCALATED | PRG-001
EQ-002 | Pfeiffer Vacuum | Turbomolecular Controller Electronics | 12 | 18 | 45% | 4 | 5 |  |  | YES | No | Controller firmware proprietary; no drop-in alt; request safety stock commitment from supplier | ESCALATED | PRG-001
EQ-003 | Thermco Systems | Tube Furnace – Hot Zone Assembly | 18 | 20 | 20% | 4 | 3 |  |  | No | No | BTU International validated as alt; maintain contact; include alt option in RFQ | MONITORED | PRG-001
EQ-003 | Thermco Systems | 8-Zone Heating Element Set | 10 | 12 | 15% | 3 | 2 |  |  | No | Yes | 2-set buffer stock maintained; supplier reliability high; no immediate action required | OK | PRG-001
EQ-004 | Tokyo Electron (TEL) | Batch Furnace – Complete System | 20 | 28 | 40% | 5 | 4 |  |  | No | No | JPY FX hedge confirmed; increase FAT scope to 3 weeks; dedicated TEL PM assigned | IN PROGRESS | PRG-001
EQ-004 | Tokyo Electron (TEL) | Process Recipe Transfer Package | N/A | N/A | 30% | 4 | 4 |  |  | YES | No | Non-tangible risk: recipe IP held by TEL; require contractual data transfer clause at PO stage | LEGAL REVIEW | PRG-001
EQ-005 | Brooks Automation | SCARA Robot – Mechanical Assembly | 12 | 14 | 15% | 3 | 3 |  |  | No | No | Brooks delivery historically reliable; no action required; standard monitoring | OK | PRG-001
EQ-005 | Brooks Automation | MES Software Integration Module | N/A | N/A | 45% | 4 | 4 |  |  | YES | No | Integration complexity risk — not supply risk; assign Brooks SW engineer on-site 4 wks pre-FAT | IN PROGRESS | PRG-001
EQ-006 | Daifuku | Overhead Track System – Civil Interface | 22 | 30 | 50% | 4 | 5 |  |  | YES | No | Civil drawings required 8 wks pre-install; freeze layout by Week 6; no alt track supplier | ESCALATED | PRG-001
EQ-007 | Air Liquide Eng. | Gas Cabinet – Complete Assembly | 16 | 22 | 40% | 3 | 3 |  |  | No | No | Quote under negotiation; delay increases if PO not placed by target date; expedite sourcing decision | IN PROGRESS | PRG-001
EQ-007 | Air Liquide Eng. | Hazmat Permit – Regulatory | N/A | N/A | 35% | 5 | 5 |  |  | YES | No | Permit lead time 8-12 wks; submit application immediately; failure impacts entire gas system install | ACTION REQ'D | PRG-001
EQ-008 | Linde Engineering | Bulk Gas Storage Vessel | 24 | 32 | 35% | 4 | 3 |  |  | No | No | Long-lead vessel; PO must be placed by program Week 4; civil pad work parallel path | IN PROGRESS | PRG-001
EQ-009 | Siemens AG | S7-1500 PLC Hardware Set | 10 | 14 | 15% | 2 | 2 |  |  | No | Yes | Strong supply reliability; buffer stock of 1 spare CPU maintained; low risk | OK | PRG-001
EQ-009 | Siemens AG | Cybersecurity Compliance Review | N/A | N/A | 25% | 3 | 3 |  |  | YES | No | Internal InfoSec review adds 3 wks; submit documentation package 6 wks pre-installation | IN PROGRESS | PRG-001
EQ-011 | ABB Ltd | 2 MVA Dry-Type Transformer | 14 | 20 | 25% | 4 | 3 |  |  | No | No | Reuse of legacy unit partially mitigates; new unit on order; monitor delivery | MONITORED | PRG-001
EQ-012 | Daikin Applied | Chiller – Complete Package | 16 | 20 | 20% | 3 | 2 |  |  | No | No | Glycol loop interface design must be finalized prior to FAT; coordinate with mechanical team | IN PROGRESS | PRG-001
EQ-014 | Applied Materials | RTP Tool – Complete System | 20 | 24 | 25% | 5 | 4 |  |  | No | No | Highest-value item; AMAT requires 30% deposit at PO; finance pre-approval gate required | ACTION REQ'D | PRG-001
EQ-015 | MiR (Mobile Industrial Robots) | AMR Fleet – 10 Units | 14 | 18 | 30% | 2 | 2 |  |  | No | No | Wi-Fi infrastructure survey required 6 wks pre-delivery; coordinate with IT/OT team | MONITORED | PRG-001
SUPPLY CHAIN RISK HEATMAP SUMMARY — PRG-001 Greenfield Expansion Phase II
Risk Tier | Count | % of Items | Action Required
CRITICAL |  |  | Immediate VP-level escalation; daily status; dedicated mitigation team
HIGH |  |  | Weekly executive review; mitigation plan required within 5 business days
MODERATE |  |  | Bi-weekly review; mitigation plan in place; monitor for deterioration
LOW |  |  | Standard monitoring; quarterly supplier check-in sufficient
AGGREGATE RISK STATISTICS — PRG-001 Greenfield Expansion Phase II
Total Components Tracked
Single-Source Components
Avg Composite Risk Score
Max Risk Score (Worst Item)
CRITICAL Tier Items
HIGH Tier Items
PRG-002 RISK REGISTER — Riverside Automation Upgrade Phase I
Equip Ref | Supplier | Component / Sub-System | Std Lead (wks) | Current Lead (wks) | Delay Prob. (0-1) | Sched. Impact (1-5) | Replace Difficulty (1-5) | Composite Risk Score | Risk Tier | Single Source? | Buffer Stock? | Mitigation Action | Status | Program ID
RV-001 | Fanuc America | Palletizing Robot – Complete Unit | 10 | 12 | 15% | 2 | 2 |  |  | No | No | Standard robot platform; low risk; monitor delivery per standard cadence | OK | PRG-002
RV-002 | Krones AG | Cartoning System – Complete Unit | 20 | 24 | 30% | 4 | 4 |  |  | YES | No | Single-source specialized tech; no qualified alt; monitor delivery weekly during build | IN PROGRESS | PRG-002
RV-003 | Fetch Robotics | AGV Fleet – Complete Units | 8 | 9 | 10% | 2 | 1 |  |  | No | No | Mature platform; low supply risk; standard monitoring | OK | PRG-002
RV-004 | Cognex Corporation | Vision Inspection – Complete Units | 6 | 7 | 10% | 2 | 1 |  |  | No | Yes | Commodity vision hardware; Keyence pre-qualified alt on file | OK | PRG-002
RV-005 | Rockwell Automation | WCS Integration – Software/Hardware | 8 | 9 | 20% | 3 | 2 |  |  | No | No | Standard PlantPAx platform; integrator has strong track record | MONITORED | PRG-002
RV-006 | Dematic Corp | Conveyor & Sortation – Complete System | 16 | 20 | 25% | 3 | 3 |  |  | No | No | Complex site-specific integration; phased cutover plan mitigates schedule risk | MONITORED | PRG-002
AGGREGATE RISK STATISTICS — PRG-002 Riverside Automation Upgrade Phase I
Total Components Tracked
Single-Source Components
Avg Composite Risk Score
Max Risk Score (Worst Item)
CRITICAL Tier Items
HIGH Tier Items

## S17_Supply_Market_Analysis
S17 — Supply Market Structure Analysis — Commodity Concentration & Pricing
Program: Greenfield Expansion Phase II ¦ Owner: Sourabh Tarodekar / Strategic Sourcing ¦ HHI = Herfindahl-Hirschman Index (sum of squared market shares x10,000) ¦ HHI > 2500 = highly concentrated market
Commodity / Category | # Global Suppliers | Top-3 Market Share (%) | HHI (Concentration Index) | 12-Mo Price Trend | Lead Time Trend | Key Market Risk / Notes
Vacuum Pumps (Turbo/Dry Screw) | 6 | 72% | 2450 | +4.2% | Extending | Pfeiffer/Edwards/Busch concentration; semiconductor demand surge
High-Temp Furnace Systems | 5 | 81% | 3100 | +6.8% | Extending | TEL/Thermco/Kokusai oligopoly; long qualification cycles limit new entrants
Precision Robotics (SCARA/6-axis) | 8 | 65% | 1980 | +2.1% | Stable | Brooks/Yaskawa/Fanuc/Kawasaki competitive field; servo chip shortage easing
Process Gas Handling Systems | 7 | 58% | 1620 | +3.5% | Extending | Air Liquide/Linde/Matheson; hazmat regulatory burden raises entry barriers
PLC / DCS Control Systems | 4 | 85% | 3400 | +1.8% | Stable | Siemens/Rockwell/ABB/Schneider dominate; software licensing model shift
Facility Power Infrastructure (Transformers) | 9 | 52% | 1340 | +8.5% | Extending | Grid-scale transformer demand surge (data centers); 18-24mo lead times industry-wide
Industrial Chillers / Cooling | 6 | 61% | 1710 | +3.0% | Stable | Daikin/Trane/Carrier; refrigerant transition (R-454B) driving redesigns
Mobile Robotics (AMR Fleets) | 10 | 48% | 1120 | -2.5% | Improving | MiR/Locus/Omron/Fetch; maturing market with price competition intensifying
MARKET INTELLIGENCE SUMMARY
Commodities Tracked
Avg HHI (Portfolio Commodities)
Highly Concentrated Markets (HHI>2500)
Avg Top-3 Market Share

## S18_Supply_Chain_Network
S18 — Supply Chain Network Map — Supplier Geography, Routes & Tier-2 Visibility
Program: Greenfield Expansion Phase II ¦ Owner: Sourabh Tarodekar / Logistics ¦ 15 suppliers across 5 countries ¦ Feeds S19 Sourcing Pipeline and S14 Cash Flow logistics timing
Supplier | Country | City / Site | Equip Ref | Transport Mode | Ocean/Intl Transit (wks) | Incoterm | Tier-2 Sub-Supplier Visibility | Customs Complexity
Edwards Vacuum | UK | Crawley | EQ-001 | Ocean + Road | 3 | DDP | Partial | Moderate — post-Brexit customs
Pfeiffer Vacuum | DE | Asslar | EQ-002 | Ocean + Road | 3 | DDP | Partial | Low — EU/US standard lanes
Thermco Systems | USA | Austin, TX | EQ-003 | Road | 1 | FOB Origin | Full | Low — domestic
Tokyo Electron Ltd | JP | Tokyo | EQ-004 | Ocean | 4 | DDP | Partial | High — JPY invoicing, import duty
Brooks Automation | USA | Chelmsford, MA | EQ-005 | Road | 1 | FOB Origin | Full | Low — domestic
Daifuku | JP | Osaka | EQ-006 | Ocean | 4 | DDP | Low — custom civil scope | High — custom project logistics
Air Liquide Engineering | FR | Frankfurt (hub) | EQ-007 | Ocean + Road | 3 | DDP | Partial | Moderate — hazmat classification
Linde Engineering | DE | Pullach | EQ-008 | Ocean + Road | 4 | DDP | Partial | Moderate — pressure vessel cert
Siemens AG | DE | Karlsruhe | EQ-009 | Ocean + Road | 3 | DDP | Full | Low — standard EU/US lanes
Inductive Automation | USA | Folsom, CA | EQ-010 | N/A — Software | 0 | N/A | Full | None — digital delivery
ABB Ltd | CH | Zurich | EQ-011 | Ocean + Road | 3 | DDP | Full | Low — standard EU/US lanes
Daikin Applied | JP | Osaka | EQ-012 | Ocean | 3 | DDP | Partial | High — JPY invoicing, import duty
Busch Vacuum | DE | Maulburg | EQ-013 | Ocean + Road | 3 | DDP | Partial | Low — EU/US standard lanes
Applied Materials | USA | Santa Clara, CA | EQ-014 | Road | 1 | FOB Origin | Full | Low — domestic
Mobile Industrial Robots (MiR) | DK | Odense | EQ-015 | Ocean + Road | 3 | DDP | Full | Moderate — EU export docs
NETWORK SUMMARY
Total Suppliers in Network
Countries Represented
Avg Ocean/International Transit (wks)
Suppliers Requiring Ocean Freight
Domestic (Road-Only) Suppliers

## S19_Strategic_Sourcing_Pipeline
S19 — Strategic Sourcing Pipeline — RFI to Award, Contract Status & Savings
Program: Greenfield Expansion Phase II ¦ Owner: Sourabh Tarodekar / Strategic Sourcing ¦ FEL = Front-End Loading (1=Concept, 2=Feasibility, 3=Definition) ¦ 12 sourcing categories tracked
Sourcing Category | Equipment Ref | FEL Phase | RFI Date | RFQ Date | Award Date | # Suppliers Bid | Awarded / Leading Supplier | Savings vs Budget (USD) | Status
Vacuum Pump Systems | EQ-001/002/013 | FEL-3 | 2024-09-15 | 2024-10-15 | 2025-01-15 | 4 | Edwards / Pfeiffer / Busch | 93000 | AWARDED
High-Temp Furnace Systems | EQ-003/004/014 | FEL-3 | 2024-08-01 | 2024-09-01 | 2025-01-01 | 3 | Thermco / TEL / AMAT | 207000 | AWARDED
Robotics & Automation | EQ-005/006/015 | FEL-3 | 2024-09-01 | 2024-10-01 | 2025-01-01 | 4 | Brooks / Daifuku / MiR | 119000 | AWARDED
Gas Handling Systems | EQ-007/008 | FEL-2 | 2024-10-01 | 2024-11-15 | 2025-02-15 (target) | 3 | Air Liquide (pending) / Linde | 22000 | IN NEGOTIATION
PLC / Control Systems | EQ-009/010 | FEL-3 | 2024-08-15 | 2024-09-15 | 2024-12-15 | 3 | Siemens / Inductive Automation | 55000 | AWARDED
Facility Infrastructure — Power | EQ-011 | FEL-3 | 2024-09-01 | 2024-10-01 | 2025-01-01 | 2 | ABB Ltd | 0 | AWARDED
Facility Infrastructure — Cooling | EQ-012 | FEL-3 | 2024-09-15 | 2024-10-15 | 2025-01-15 | 3 | Daikin Applied | 41000 | AWARDED
Spare Parts & Consumables | S23 register | FEL-2 | 2025-01-15 | 2025-02-15 | 2025-04-01 (target) | 5 | Multiple | 0 | IN PROGRESS
Field Service Contracts | All platforms | FEL-1 | 2025-02-01 | 2025-03-01 (target) | TBD | — | TBD | 0 | PLANNED
Alt-Source Qualification — TMP | EQ-002 | FEL-2 | 2025-02-01 | 2025-03-01 | 2025-06-01 (target) | 1 | Shimadzu (qualifying) | 0 | IN QUALIFICATION
Alt-Source Qualification — Gas Cabinet | EQ-007 | FEL-1 | 2025-03-01 | TBD | TBD | 1 | Matheson Gas (RFQ issued) | 0 | RFQ ISSUED
IT/OT Network Infrastructure | EQ-009/010 DMZ | FEL-2 | 2025-04-15 | 2025-05-01 | 2025-06-01 (target) | 3 | TBD | 0 | IN PROGRESS
SOURCING PIPELINE SUMMARY
Total Sourcing Categories
Categories Awarded
Categories In Progress / Negotiation
Total Savings vs Budget (USD)
Avg Suppliers Bid per Category

## S20_Dual_MultiSource_Strategy
S20 — Dual / Multi-Source Strategy — Qualification Status & Risk Reduction
Program: Greenfield Expansion Phase II ¦ Owner: Sourabh Tarodekar / Strategic Sourcing ¦ 8 commodities with active or completed dual-source programs ¦ Directly reduces S16 supply chain risk exposure
Commodity | Primary Supplier | Equip Ref | Alternate Supplier | Qualification Status | Risk Reduction Rationale | Target Completion | Notes
Turbomolecular Pumps | Pfeiffer Vacuum | EQ-002 | Shimadzu Corp (TMP-3203L) | IN QUALIFICATION | Eliminates single-source CRITICAL risk on program's highest-risk item | 2025-Q3 | 90-day qualification program initiated per CR-007; test units requested
Dry Screw Vacuum Pumps | Edwards Vacuum | EQ-001 | Busch Vacuum | AVL — QUALIFIED | Already-qualified alt reduces post-Brexit logistics exposure | COMPLETE | Busch already supplies EQ-013; cross-qualified as backup to Edwards
High-Temp Tube Furnaces | Thermco Systems | EQ-003 | BTU International | AVL — QUALIFIED | Reduces exposure to single furnace OEM for core process step | COMPLETE | BTU pre-qualified; compatible process performance confirmed
Batch Oxidation Furnaces | Tokyo Electron Ltd | EQ-004 | Kokusai Electric | PRE-QUALIFIED | Mitigates JPY/TEL concentration risk on second-largest CapEx line | 2025-Q4 (monitoring) | Pre-qualified but not activated; TEL relationship strategic, monitored not urgent
Process Gas Cabinets | Air Liquide Engineering | EQ-007 | Matheson Gas | RFQ ISSUED | Provides commercial leverage during active EQ-007 negotiation | 2025-Q2 | RFQ issued in parallel with Air Liquide negotiation; pricing/delivery under review
Bulk Gas Storage & Delivery | Linde Engineering | EQ-008 | Air Products | RFQ ISSUED | Commercial leverage; long lead-time category benefits from dual-source | 2025-Q3 | Used as competitive tension during Linde negotiation (closed favorably)
SCARA Robots | Brooks Automation | EQ-005 | Kawasaki Robotics | TECHNICAL EVAL | Reduces dependency on single robotics OEM for material handling | 2025-Q4 | Technical evaluation only; no immediate qualification driver — moderate priority
Roots Blower Boosters | Busch Vacuum | EQ-013 | Edwards Vacuum | AVL — QUALIFIED | Mutual cross-qualification with EQ-001 Edwards / EQ-013 Busch pairing | COMPLETE | Edwards and Busch mutually qualified as alternates across both platforms
DUAL-SOURCE PROGRAM IMPACT SUMMARY
Commodities with Dual-Source Program
Qualified / AVL-Ready Alternates
Active Qualification Programs
RFQ / Early-Stage Programs

## S21_Negotiation_Tracker
S21 — Negotiation Tracker — Commercial Negotiation Log & Savings Portfolio
Tracks all active and completed negotiations ¦ Owner: Sourabh Tarodekar ¦ BATNA = Best Alternative to Negotiated Agreement ¦ Feeds S19 Strategic Sourcing Pipeline
Neg ID | Supplier | Category | Contract Value | Neg Type | Start | Close | Initial Quote (USD) | Internal Target (USD) | Walk-Away (USD) | Key Leverage | BATNA | Final Agreed (USD) | Savings (USD) | Savings % | Status
N-001 | Pfeiffer Vacuum | TMP Systems (EQ-002) | 930000 | Initial Award | 2024-Q4 | 2025-Q1 | 975000 | 920000 | 1000000 | Single-source risk acknowledged; Shimadzu qual threat | Shimadzu TMP-3203L qualification | 930000 |  |  | CLOSED
N-002 | Thermco Systems | Tube Furnaces (EQ-003) | 1040000 | Competitive Award | 2024-Q3 | 2024-Q4 | 1122000 | 1030000 | 1180000 | BTU International valid alt; multi-unit volume | BTU International — pre-qualified | 1040000 |  |  | CLOSED
N-003 | Applied Materials | RTP Tool (EQ-014) | 1750000 | Strategic Negotiation | 2024-Q2 | 2025-Q1 | 1875000 | 1720000 | 1900000 | Multi-unit commitment (2 units); Phase III expansion signal | TEL — RTP alternative evaluated | 1750000 |  |  | CLOSED
N-004 | Brooks Automation | SCARA Robots (EQ-005) | 1650000 | Competitive Award | 2024-Q3 | 2024-Q4 | 1745000 | 1630000 | 1800000 | 6-unit volume; Kawasaki technical evaluation in parallel | Kawasaki Robotics — technical eval | 1650000 |  |  | CLOSED
N-005 | Siemens AG | DCS Platform (EQ-009) | 825000 | LTA Renewal | 2023-Q4 | 2024-Q1 | 880000 | 810000 | 920000 | Existing relationship; Phase II expansion commitment; SCADA alt | Rockwell Automation as alt DCS | 825000 |  |  | CLOSED — LTA active
N-006 | Air Liquide Eng. | Gas Cabinets (EQ-007) | TBC (target) | Active Negotiation | 2025-Q1 | 2025-Q2 target | 840000 | 760000 | 850000 | Matheson Gas RFQ in parallel; hazmat permit dependency | Matheson Gas — RFQ issued parallel | TBC | TBC | TBC | IN NEGOTIATION
N-007 | Linde Engineering | Bulk Gas (EQ-008) | 340000 | Competitive Award | 2024-Q4 | 2025-Q1 | 362000 | 330000 | 380000 | Existing site contract leverage; 32-wk LT accepted | Air Products — RFQ issued | 340000 |  |  | CLOSED
N-008 | Edwards Vacuum | Dry Screw Pumps (EQ-001) | 740000 | Competitive — Dual Source | 2024-Q4 | 2025-Q1 | 788000 | 725000 | 810000 | Busch as dual-source alt; volume split threat | Busch Vacuum — already qualified | 740000 |  |  | CLOSED
N-009 | Daikin Applied | Process Chillers (EQ-012) | 885000 | Competitive Award | 2024-Q4 | 2025-Q1 | 926000 | 870000 | 950000 | Carrier as competitive alt; glycol loop specification leverage | Carrier Corporation | 885000 |  |  | CLOSED
N-010 | Mobile Industrial Robots | AMR Fleet (EQ-015) | 380000 | Competitive Award | 2024-Q4 | 2025-Q1 | 404000 | 370000 | 420000 | Locus Robotics and Omron in parallel eval; fleet SW requirement | Omron AMR — evaluated but lower capability | 380000 |  |  | CLOSED
SAVINGS PORTFOLIO SUMMARY
Total Negotiations Logged
Closed Negotiations
Total Confirmed Savings (Closed Negotiations, USD)
Average Savings % (vs Initial Quote, Closed Only)

## S22_Capacity_Supplier_Facing
S22 — Supplier Capacity Assessment — Program Demand vs Supplier Available Capacity
Identifies capacity concentration risk at supplier level ¦ Owner: Sourabh Tarodekar ¦ Complements S10 Capacity Planning (equipment-side view) with a supply-side capacity view
Equip Ref | Supplier | Component | Est. Supplier Annual Capacity (units/yr) | Program Volume Required (units/yr) | % of Supplier Capacity Consumed | Capacity Constraint Risk | Lead Time to Add'l Capacity (wks) | Flex Capacity Available (units) | MOQ | Order Frequency | Safety Stock Coverage (wks) | Buffer Recommendation | Notes
EQ-001 | Edwards Vacuum | Dry Screw Vacuum Pumps | 120 | 4 |  | LOW | 16 | 20 | 1 | Per program | 8 | 2-unit buffer on-site | Edwards produces ~120 units/yr globally; 4 units = low concentration
EQ-002 | Pfeiffer Vacuum | Turbomolecular Pumps | 60 | 3 |  | HIGH | 18 | 10 | 1 | Per program | 12 | 2-unit safety stock critical | Pfeiffer TMP production ~60 units/yr globally; 3 units = 5% of output. Supply constraint at volume. Alt qualification essential.
EQ-003 | Thermco Systems | High-Temp Tube Furnaces | 45 | 2 |  | LOW-MOD | 20 | 8 | 1 | Per program | 10 | 1 spare hot-zone set | Thermco capacity adequate; BTU alt available
EQ-004 | Tokyo Electron Ltd | Batch Oxidation Furnaces | 150 | 2 |  | LOW | 24 | 15 | 1 | Per program | 14 | Coordinated with TEL FSE | TEL large OEM; 2 units = minimal fraction of global capacity
EQ-005 | Brooks Automation | SCARA Robots | 800 | 6 |  | VERY LOW | 12 | 50 | 2 | Per program | 6 | Standard stock level | Brooks Automation high-volume producer; 6 units trivial
EQ-006 | Daifuku | Overhead Track Conveyor | 25 | 1 |  | MOD — custom design | 30 | 5 | 1 | Per project | 0 | No standard buffer — custom | Each Daifuku conveyor is a custom civil project; capacity = design+install bandwidth, not inventory
EQ-007 | Air Liquide Eng. | Process Gas Cabinets | 200 | 4 |  | LOW | 16 | 20 | 1 | Per program | 8 | 1 spare manifold assembly | Air Liquide Eng. large manufacturer; 4 units = low share
EQ-008 | Linde Engineering | Bulk Gas Storage Vessels | 80 | 1 |  | LOW | 28 | 5 | 1 | Per program | 0 | Long-lead only — no buffer | Vessel is bespoke; 32-wk LT is design/fabrication not inventory
EQ-009 | Siemens AG | DCS PLC S7-1500 | 50000 | 5 |  | VERY LOW | 10 | 500 | 5 | Annual blanket | 12 | Standard depot stock — Siemens USA | Mass-manufactured; 5 units = negligible supply risk
EQ-010 | Inductive Automation | SCADA Software Licenses | Unlimited (SaaS) | 3 | N/A | VERY LOW | 0 | N/A | 1 | On demand | 0 | Software — no physical buffer needed | SaaS-adjacent model; license delivery instantaneous
EQ-011 | ABB Ltd | Dry-Type Transformers | 300 | 2 |  | LOW | 18 | 10 | 1 | Per program | 0 | Long-lead; no buffer practical | ABB large transformer OEM; 2 units = negligible share
EQ-012 | Daikin Applied | Process Chiller Systems | 400 | 3 |  | LOW | 18 | 15 | 1 | Per program | 6 | Standard refrigerant spares kit | Daikin Applied large US/JP manufacturer; low concentration
EQ-013 | Busch Vacuum | Roots Blower Boosters | 250 | 6 |  | LOW | 14 | 20 | 1 | Per program | 8 | 2-unit buffer coordinated with EQ-001 | Busch high-volume vacuum manufacturer; 6 units = low share
EQ-014 | Applied Materials | RTP Tools | 40 | 2 |  | MOD-HIGH | 24 | 5 | 1 | Per program | 0 | No buffer — high-value; 30% deposit commitment | AMAT RTP production limited; 2 units = notable share. Finance pre-approval required.
EQ-015 | Mobile Industrial Robots | AMR Fleet (x10 robots) | 5000 | 10 |  | VERY LOW | 14 | 100 | 10 | Per program | 0 | Standard warranty + software update coverage | MiR high-volume AMR producer; 10 units negligible

## S23_Inventory_Buffer_Planning
S23 — Inventory & Buffer Planning — Consumables, Spare Parts & Safety Stock
Covers production consumables, critical spares (MTBF/MTTR model), and safety stock ¦ Owner: Sourabh Tarodekar ¦ Carrying cost = 20% ¦ Production value from S01_Disclaimer_Assumptions
SECTION A — CRITICAL SPARE PARTS (MTBF / MTTR MODEL)
Part ID | Part Description | Equip Ref | Supplier | Class | MTBF (hrs) | MTTR (hrs) | Annual Failures (Est.) | Safety Stock (units) | Unit Cost (USD) | Annual Consumption (units) | Inventory Value (USD) | Annual Carry Cost (20%) | Downtime Avoidance (hrs/yr) | Annual Downtime Value Avoided (USD/yr) | Notes
SP-001 | Dry Screw Pump Seal Set | EQ-001 | Edwards Vacuum | A | 8760 | 4 | 1 | 2 | 3200 | 2 |  |  |  |  | Seals degrade; annual replacement expected; 2-set safety stock
SP-002 | Turbomolecular Pump Bearing | EQ-002 | Pfeiffer Vacuum | A | 4380 | 8 | 2 | 2 | 8500 | 4 |  |  |  |  | CRITICAL — bearing failure = tool down; 2-set stock maintained
SP-003 | Turbomolecular Pump Controller | EQ-002 | Pfeiffer Vacuum | A | 8760 | 16 | 1 | 1 | 12000 | 1 |  |  |  |  | Proprietary controller; no drop-in alt; Pfeiffer safety stock commitment
SP-004 | Furnace Heating Elements (8-zone set) | EQ-003 | Thermco Systems | B | 4380 | 6 | 2 | 2 | 4800 | 4 |  |  |  |  | Zone element failure predictable; 2-set buffer; 2-4 wk replacement
SP-005 | Batch Furnace Process Tube | EQ-004 | Tokyo Electron Ltd | B | 8760 | 12 | 1 | 1 | 6500 | 1 |  |  |  |  | Quartz tube — 12-wk lead time from TEL; must stock 1 spare
SP-006 | SCARA Robot Servo Drive | EQ-005 | Brooks Automation | B | 8760 | 4 | 1 | 2 | 3800 | 2 |  |  |  |  | Drive failure low frequency; 2-unit stock adequate
SP-007 | Gas Cabinet MFC Assembly | EQ-007 | Air Liquide Eng. | A | 4380 | 8 | 2 | 2 | 5200 | 4 |  |  |  |  | MFC drift = recalibration or replacement; high-use spare
SP-008 | DCS CPU Module — S7-1500 | EQ-009 | Siemens AG | A | 43800 | 2 | 0.2 | 2 | 4200 | 1 |  |  |  |  | CPU failure rare; 2 on-site + Siemens depot replenishment
SP-009 | Chiller Compressor Capacitor Kit | EQ-012 | Daikin Applied | C | 8760 | 2 | 1 | 2 | 850 | 2 |  |  |  |  | Capacitor kit; standard maintenance item; low cost
SP-010 | RTP Lamp Array (set of 12) | EQ-014 | Applied Materials | A | 4380 | 8 | 2 | 2 | 18500 | 4 |  |  |  |  | Highest-value spare; AMAT recommends 2-set safety stock; 8-wk LT
SP-011 | AMR Battery Pack | EQ-015 | MiR | C | 4380 | 1 | 2 | 4 | 1200 | 8 |  |  |  |  | Battery degradation predictable; 4-pack standard; MiR swap warranty
SP-012 | Roots Blower Booster Rotor | EQ-013 | Busch Vacuum | B | 8760 | 6 | 1 | 1 | 2800 | 1 |  |  |  |  | Coordinated with Edwards EQ-001 maintenance schedule
SPARE PARTS TOTAL
SECTION B — PRODUCTION CONSUMABLES & RAW MATERIALS
Item ID | Item Description | Category | Supplier | Lead Time (wks) | Avg Weekly Demand (units) | Demand Std Dev | Service Level Target | Safety Stock (units) | Reorder Point (units) | EOQ (units) | Current Stock | Unit Cost (USD) | Inventory Value (USD) | Notes
CM-001 | Process N2 Gas (cylinder sets) | Process Gas | Air Liquide / Linde | 2 | 12 | 3 | 98% | 10 | 34 | 50 | 45 | 380 |  | High-consumption; order weekly; dual-source reduces stockout risk
CM-002 | Quartz Process Tubes (spare) | Process Consumable | Heraeus / Shin-Etsu | 6 | 0.5 | 0.2 | 99% | 4 | 7 | 6 | 8 | 2200 |  | Long-lead quartz; 6-wk LT drives high safety stock
CM-003 | Photoresist (process grade) | Process Chemical | JSR Corporation | 4 | 8 | 2.5 | 99% | 10 | 42 | 60 | 55 | 1800 |  | High-value chemical; 4-wk LT; temperature-controlled storage
CM-004 | Argon Gas (bulk, per cylinder) | Process Gas | Linde Engineering | 1 | 6 | 1.5 | 97% | 5 | 17 | 40 | 30 | 290 |  | Low risk; Linde on-site contract; auto-replenishment
CM-005 | Chemical Mechanical Planarization Slurry | Process Chemical | Cabot Microelectronics | 3 | 4 | 1.5 | 99% | 8 | 20 | 40 | 25 | 1500 |  | Specialty chemical; 2 approved sources; shelf life 6 months
CM-006 | Cleaning Solvents (IPA, Acetone) | Facility Chemical | VWR / Fisher Scientific | 1 | 10 | 3 | 95% | 8 | 18 | 80 | 65 | 45 |  | Commodity; easy dual-source; low-cost; broad availability
CONSUMABLES TOTAL

## S24_Asset_Tracking
S24 — Asset Tracking Register — Equipment Fleet Lifecycle & Physical Status
Tracks all 45 physical assets by serial/tag, location, lifecycle state, maintenance & warranty ¦ Owner: Sourabh Tarodekar ¦ Register is platform-level (15 rows); Qty column expands to 45 physical units total ¦ Feeds S29 ROI Tracker and S25 Milestone Gate Tracker
Asset Tag | Equip Ref | Asset Description | Serial # (Synthetic) | Qty | Location (Zone/Bay) | Current Status | Purchase Date | Install Date | Commiss. Date | Remaining Lifetime (yrs) | Replace Target Year | Replacement Cost Est. (USD) | Warranty Expiry | Support Contract | Notes
AST-001 | EQ-001 | Dry Screw Vacuum Pump (x4) | VSP-2025-001/004 | 4 | Bay A — Vacuum Zone | IN PRODUCTION | 2025-02-15 | 2025-09-01 | 2025-11-15 | 10 | 2035 | 890000 | 2025-Q4 (see contract) | Edwards Annual PM | Post-Brexit logistics; Busch backup activated
AST-002 | EQ-002 | Turbomolecular Pump (x3) | TMP-2025-101/103 | 3 | Bay A — Vacuum Zone | IN PRODUCTION | 2025-02-20 | 2025-11-01 | 2025-12-15 | 8 | 2033 | 1200000 | 2025-Q4 (see contract) | Pfeiffer 24/7 support | CRITICAL path item; bearing safety stock maintained
AST-003 | EQ-003 | Tube Furnace System (x2) | THF-2025-201/202 | 2 | Bay B — Thermal Zone | IN PRODUCTION | 2025-01-20 | 2025-09-15 | 2025-11-20 | 13 | 2038 | 1350000 | 2025-Q4 (see contract) | Thermco 3yr full service | FAT completed Austin TX; recipe transfer done
AST-004 | EQ-004 | Batch Oxidation Furnace (x2) | BOF-2025-301/302 | 2 | Bay B — Thermal Zone | QUALIFIED — PQ in progress | 2025-02-10 | 2025-11-15 | Pending | 13 | 2038 | 1700000 | 2025-Q4 (see contract) | TEL 3yr comprehensive | JPY FX hedged; structural reinforcement complete
AST-005 | EQ-005 | SCARA Robot (x6) | SCR-2025-401/406 | 6 | Bay C — Robotics Zone | IN PRODUCTION | 2025-01-15 | 2025-09-01 | 2025-11-10 | 8 | 2033 | 2200000 | 2025-Q4 (see contract) | Brooks MES+mech 2yr | MES integration verified; OEE above plan
AST-006 | EQ-006 | Overhead Conveyor (x1 system) | OTC-2025-501 | 1 | Bays A-C — Overhead Track | INSTALLED — commissioning | 2025-02-20 | 2025-11-20 | Pending | 10 | 2035 | 560000 | 2025-Q4 (see contract) | Daifuku civil+mech 2yr | Civil interface complete; Wi-Fi nav calibration in progress
AST-007 | EQ-007 | Process Gas Cabinet (x4) | PGC-2025-601/604 | 4 | Bay D — Gas Room | IN PRODUCTION | 2025-02-28 | 2025-10-01 | 2025-11-30 | 10 | 2035 | 1040000 | 2025-Q4 (see contract) | Air Liquide annual cert | Hazmat permit closed; MFC calibration schedule active
AST-008 | EQ-008 | Bulk Gas Storage (x1 system) | BGS-2025-701 | 1 | External — Tank Farm | IN PRODUCTION | 2025-02-20 | 2025-11-10 | 2025-12-01 | 18 | 2043 | 450000 | 2025-Q4 (see contract) | Linde site contract | 32-wk LT; on-site Linde maintenance contract
AST-009 | EQ-009 | DCS — Siemens S7-1500 (x5) | DCS-2025-801/805 | 5 | Control Room | IN PRODUCTION | 2025-01-28 | 2025-09-01 | 2025-11-01 | 8 | 2033 | 1100000 | 2025-Q4 (see contract) | Siemens Gold Support | Cybersecurity audit Month 4; LTA pricing locked
AST-010 | EQ-010 | SCADA Platform (x3 licenses) | SCA-2025-901/903 | 3 | Control Room (virtual) | IN PRODUCTION | 2025-02-05 | 2025-09-01 | 2025-11-01 | 6 | 2031 | 330000 | 2025-Q4 (see contract) | Inductive Auto subscription | Annual license renewal; IT/OT integration stable
AST-011 | EQ-011 | Dry-Type Transformer (x2) | TRF-2025-1001/1002 | 2 | Electrical Room | IN PRODUCTION | 2025-02-01 | 2025-08-15 | 2025-10-01 | 23 | 2048 | 560000 | 2050-02-01 | ABB manufacturer warranty | Reused partial from prior program; new units installed
AST-012 | EQ-012 | Process Chiller (x3) | PCH-2025-1101/1103 | 3 | Mechanical Room | IN PRODUCTION | 2025-01-30 | 2025-09-15 | 2025-11-20 | 13 | 2038 | 1150000 | 2025-Q4 (see contract) | Daikin annual PM | Glycol loop stable; JPY FX hedged
AST-013 | EQ-013 | Roots Blower Booster (x6) | RBB-2025-1201/1206 | 6 | Bay A — Vacuum Zone | IN PRODUCTION | 2025-01-28 | 2025-09-01 | 2025-11-15 | 8 | 2033 | 975000 | 2025-Q4 (see contract) | Busch annual PM | Paired with EQ-001; coordinated maintenance schedule
AST-014 | EQ-014 | RTP Tool (x2) | RTP-2025-1301/1302 | 2 | Bay B — Thermal Zone | IN PRODUCTION | 2025-02-01 | 2025-10-20 | 2025-12-01 | 10 | 2035 | 2300000 | 2025-Q4 (see contract) | AMAT comprehensive 3yr | Highest-value asset; AMAT dedicated FSE on-site Q4-2025
AST-015 | EQ-015 | AMR Fleet (x10 robots) | AMR-2025-1401/1410 | 10 | All Bays — Fleet routing | IN PRODUCTION | 2025-02-05 | 2025-09-15 | 2025-11-15 | 6 | 2031 | 500000 | 2025-Q4 (see contract) | MiR fleet management sub | Wi-Fi integration stable; Phase 2 routing optimization pending
FLEET SUMMARY
Total Assets Tracked (sum of Qty)
Equipment Platforms
Assets In Production (platforms)
Total Replacement Value (Portfolio, USD)
Average Remaining Lifetime (yrs)

## S25_Milestone_Gate_Tracker
S25 — Program Milestone & Gate Review Tracker — Greenfield Expansion Phase II
Gate-controlled program: G0 Concept -> G1 Definition -> G2 Execution -> G3 Commissioning -> G4 Qualification -> G5 Production Release ¦ All gate entry criteria must be GREEN before approval; AMBER items require documented acceptance; RED items are blockers.
GATE REVIEW STATUS SUMMARY
Gate | Gate Name | Target Date | Actual/Forecast Date | Gate Status | Entry Criteria Met | Approver | Approval Date | Open Blockers (count) | Decision | Notes
G0 | Program Concept & Business Case | 2025-02-28 | 2025-03-10 | APPROVED | 100% | VP Engineering + CFO | 2025-03-10 | 0 | GO | Business case approved. Scenario B selected. AR-2025-0082 submitted. All G0 criteria met.
G1 | Supplier Selection & AR Approval | 2025-04-07 | 2025-04-05 | APPROVED | 95% | VP Engineering + CFO | 2025-04-07 | 1 | CONDITIONAL GO | AR approved. All POs placed except EQ-007 (Air Liquide quote negotiation ongoing). Conditional GO: EQ-007 PO must be placed within 2 weeks.
G2 | Equipment Build & FAT Complete | 2025-09-01 | 2025-09-08 | IN PROGRESS | 60% | Director of Engineering | TBD | 3 | PENDING | EQ-003 FAT complete. EQ-004, EQ-014 FAT scheduled. EQ-002 at risk due to Pfeiffer lead time. 3 open blockers: EQ-002 delivery, EQ-007 hazmat permit, EQ-006 civil drawing freeze.
G3 | Site Installation & Utility Commissioning | 2025-10-27 | 2025-10-27 | NOT STARTED | 0% | Program Manager | TBD | 0 | TBD | Gate G3 not yet in scope. Entry criteria to be reviewed at G2 approval. Key dependency: all equipment delivered and installed; utility hookup complete.
G4 | Process Qualification (PQ) Complete | 2025-11-24 | 2025-11-24 | NOT STARTED | 0% | Director of Engineering | TBD | 0 | TBD | Gate G4 requires: PQ protocol approved; first-article wafer data reviewed; yield >94%; equipment uptime demonstrated >90% over 30-day window.
G5 | Production Release & Ramp | 2025-12-08 | 2025-12-08 | NOT STARTED | 0% | VP Engineering | TBD | 0 | TBD | Gate G5 requires: G4 approved; SOP training complete; spare parts inventory stocked; maintenance schedule published; manufacturing handover signed off.
DETAILED PROGRAM MILESTONES
Milestone ID | Gate | Milestone Description | Equipment Ref | Planned Date | Forecast Date | Actual Date | Owner | Status | % Complete | Predecessor | Notes
M-001 | G0 | Business case and scenario analysis | ALL | 2025-03-10 | 2025-03-10 | 2025-03-10 | Sourabh Tarodekar | COMPLETE | 100% | — | Scenario B approved; S13 model signed off by Finance
M-002 | G0 | Capital AR (AR-2025-0082) submitted to Finance | ALL | 2025-03-19 | 2025-03-19 | 2025-03-19 | R. Patel | COMPLETE | 100% | M-001 | AR submitted with full TCO and NPV justification
M-003 | G1 | AR approval received from VP Eng + CFO | ALL | 2025-04-07 | 2025-04-05 | 2025-04-05 | Sourabh Tarodekar | COMPLETE | 100% | M-002 | Approved ahead of schedule — enables early PO placement
M-004 | G1 | Long-lead POs placed (EQ-002, EQ-004, EQ-008, EQ-014) | Multiple | 2025-04-07 | 2025-04-05 | 2025-04-05 | S. Kim | COMPLETE | 100% | M-003 | All 4 long-lead POs placed. Supplier delivery schedules confirmed.
M-005 | G1 | EQ-007 hazmat permit application filed | EQ-007 | 2025-03-24 | 2025-03-22 | 2025-03-22 | D. Walsh | COMPLETE | 100% | M-003 | Filed 2 days early. Consultant engaged. Permit approval pending.
M-006 | G1 | All remaining equipment POs placed | Multiple | 2025-04-21 | 2025-04-18 | 2025-04-18 | S. Kim | COMPLETE | 100% | M-003 | 11 remaining POs placed. Full portfolio committed.
M-007 | G1 | FX hedge contracts executed (EUR + JPY) | EQ-004/007 | 2025-05-08 | 2025-05-08 | 2025-05-08 | R. Patel | COMPLETE | 100% | M-004 | Forward contracts locked. EUR 1.09, JPY 149.0.
M-008 | G2 | EQ-003 Thermco FAT complete | EQ-003 | 2025-07-14 | 2025-07-14 | — | M. Chen | IN PROGRESS | 40% | M-006 | Protocol approved. FAT scheduled Week 22. Recipe transfer plan agreed.
M-009 | G2 | EQ-001 & EQ-013 pump FATs complete | EQ-001/013 | 2025-07-28 | 2025-07-28 | — | S. Kim | NOT STARTED | 0% | M-006 | Coordinated FAT schedule required; confirm with both suppliers
M-010 | G2 | EQ-004 TEL batch furnace FAT complete (Japan) | EQ-004 | 2025-08-11 | 2025-08-18 | — | M. Chen | AT RISK | 15% | M-006 | Extended lead time (28 wks) puts FAT at Week 29 — 1 week behind plan
M-011 | G2 | EQ-014 AMAT RTP FAT complete | EQ-014 | 2025-08-04 | 2025-08-04 | — | M. Chen | IN PROGRESS | 25% | M-004 | AMAT FAT protocol approved. Edge ring lot included. Site visit booked.
M-012 | G2 | EQ-002 Pfeiffer TMP FAT complete | EQ-002 | 2025-08-18 | 2025-09-01 | — | S. Kim | AT RISK | 5% | M-004 | CRITICAL: 26-wk LT pushes FAT to Week 30. Single-source risk active.
M-013 | G2 | EQ-007 hazmat permit received | EQ-007 | 2025-05-30 | 2025-05-30 | — | D. Walsh | IN PROGRESS | 50% | M-005 | Consultant tracking. Risk of 2-week overrun if permit delayed.
M-014 | G2 | EQ-006 conveyor civil drawings frozen | EQ-006 | 2025-05-19 | 2025-05-19 | — | T. Okonkwo | IN PROGRESS | 80% | M-006 | Layout review in progress. Freeze confirmed by Week 6.
M-015 | G3 | All equipment delivered to site | ALL | 2025-09-08 | 2025-09-08 | — | S. Kim | NOT STARTED | 0% | M-012 | Delivery schedule contingent on EQ-002 and EQ-004 manufacturing completion
M-016 | G3 | Site electrical sub-panel installation | EQ-001 | 2025-08-18 | 2025-08-18 | — | T. Okonkwo | IN PROGRESS | 35% | M-006 | Contractor engaged. Sub-panel installation Weeks 28-29.
M-017 | G3 | EQ-004 structural floor reinforcement complete | EQ-004 | 2025-07-28 | 2025-07-28 | — | T. Okonkwo | IN PROGRESS | 70% | M-006 | Structural work underway. External crane booked.
M-018 | G3 | All equipment installation and utility hookup complete | ALL | 2025-10-13 | 2025-10-13 | — | T. Okonkwo | NOT STARTED | 0% | M-015 | 4 wks install + 2 wks utility hookup per platform; parallel paths planned
M-019 | G4 | Process qualification (PQ) initiated — first tool | EQ-014 | 2025-10-27 | 2025-10-27 | — | M. Chen | NOT STARTED | 0% | M-018 | EQ-014 RTP first to PQ; edge ring data from FAT will accelerate PQ
M-020 | G4 | Process qualification (PQ) complete — all tools | ALL | 2025-11-24 | 2025-11-24 | — | M. Chen | NOT STARTED | 0% | M-019 | 5-week PQ phase; yield >94% and uptime >90% required
M-021 | G5 | Manufacturing handover and production release | ALL | 2025-12-08 | 2025-12-08 | — | A. Novak | NOT STARTED | 0% | M-020 | SOP training, spare parts stocked, maintenance schedule published
PROGRAM PROGRESS SUMMARY
Total Milestones
Milestones Complete
Milestones In Progress
Milestones At Risk or Blocked
Overall Program %
Gates Complete / Approved
Open Blockers Across All Gates

## S26_Engineering_Change_Orders
S26 — Engineering Change Orders (ECO) Register — Phase II Program
Formal ECO register for all design changes — internal, customer-driven & regulatory ¦ Owner: Sourabh Tarodekar ¦ Related VDCs tracked in S27_Vendor_Design_Changes
ECO ID | ECO Title | Originator | Origin Type | Affected Equip | Change Description | Reason | Cost Impact (USD) | Schedule Impact (wks) | Quality/Yield Impact | Requalif. Required? | ECO Status | Design Auth. Approval Date | Submitted Date | Impl. Date | Linked VDC
ECO-001 | Gas Cabinet Safety Interlock Upgrade | Facilities / Safety | Regulatory | EQ-007 | Add secondary pressure interlock and emergency shutoff valve per updated NFPA 72 guidance | Regulatory compliance — permit condition | 28500 | 2 | No yield impact; safety-critical improvement | YES — re-FAT on gas cabinet | IMPLEMENTED | 2025-03-10 | 2025-03-24 | 2025-05-15 | —
ECO-002 | TEL Furnace Recipe Parameter Change | Process Engineering | Customer-Driven | EQ-004 | Update oxidation time profile on Recipe Set B3 to achieve customer-specified film uniformity +/-1.5% | Customer quality requirement tightened for Phase III product | 12000 | 1 | Yield improvement expected +0.5% on PF-A | YES — PQ re-run for Recipe B3 | IMPLEMENTED | 2025-04-02 | 2025-04-08 | 2025-07-20 | VDC-003
ECO-003 | RTP Edge Ring Material Substitution | Process Engineering / AMAT | Internal Engineering | EQ-014 | Replace SiC edge ring with high-purity CVD SiC — improved thermal uniformity at >900C | Process optimization — reduce edge exclusion zone | 15000 | 0 | Yield improvement +0.8% at wafer edge | YES — thermal profile re-validation | IMPLEMENTED | 2025-02-15 | 2025-02-28 | 2025-06-10 | VDC-001
ECO-004 | MES Integration Protocol Revision | Controls / IT-OT | Internal Engineering | EQ-005/009/010 | Update SCADA-to-MES data handshake to use REST API v2.1 (replace deprecated SOAP endpoints) | IT/OT architecture upgrade — eliminates latency bug | 8000 | 1 | No yield impact; +15ms improvement in alarm response | NO — software change only | IMPLEMENTED | 2025-05-10 | 2025-05-17 | 2025-07-01 | —
ECO-005 | Chiller Glycol Concentration Adjustment | Facilities Engineering | Internal Engineering | EQ-012 | Increase inhibited glycol concentration from 30% to 35% to reduce corrosion in stainless loop | Preventive — loop inspection found minor oxidation at fittings | 3500 | 0 | No yield impact; improved system longevity | NO | IMPLEMENTED | 2025-06-01 | 2025-06-05 | 2025-06-15 | —
ECO-006 | Dry Screw Pump N2 Purge Line Upgrade | Engineering / Edwards | Internal Engineering | EQ-001/013 | Increase N2 purge flow from 8 L/min to 12 L/min to reduce pump seal degradation rate | Reliability improvement — seal MTBF extended by ~20% | 18000 | 1 | No yield impact; MTBF improvement 8,760 -> 10,500 hrs | NO — purge line change only | IN REVIEW | 2025-07-12 | Pending | TBC | —
ECO-007 | DCS Cybersecurity Firmware Update | Controls / InfoSec | Regulatory | EQ-009 | Apply Siemens TIA Portal firmware patch v19.0.3 per ICS-CERT advisory ICSA-2025-089 | Security patch — critical vulnerability mitigation | 5000 | 0 | No yield impact; mandatory security update | NO — firmware only; controlled change | IN REVIEW | 2025-07-20 | Pending | 2025-08-15 target | —
ECO-008 | AMR Fleet Route Optimization v2 | Operations / MiR | Internal Engineering | EQ-015 | Implement MiR Fleet Manager route algorithm Phase 2 to reduce carrier wait time by ~18% | Operational efficiency — program improvement | 6000 | 0 | No yield impact; +18% throughput improvement for AMR | NO — software update | IMPLEMENTED | 2025-08-01 | 2025-08-05 | 2025-09-01 | —
ECO-009 | Bulk Gas Vessel Pressure Relief Resetting | Safety / Linde | Regulatory | EQ-008 | Recalibrate PRV setpoints from 320 PSI to 300 PSI per updated site pressure vessel code | Regulatory requirement — insurance inspection finding | 4200 | 0 | No yield impact; safety compliance | YES — pressure test re-cert required | IN REVIEW | 2025-08-10 | Pending | 2025-09-15 target | VDC-005
ECO-010 | Furnace Zone Controller Firmware Upgrade | Process Engineering / Thermco | Internal Engineering | EQ-003 | Upgrade Thermco zone controller firmware v4.1->v4.3 for improved PID auto-tune algorithm | Process stability improvement — temperature uniformity +/-0.3C better | 7000 | 0 | Yield improvement expected +0.2% | YES — process re-qualification run required | DRAFT | 2025-09-05 | Pending | TBC | —
ECO SUMMARY
Total ECOs Raised
Implemented / Closed
In Review
Total Cost Impact (USD)
Requalification Required (count of YES)

## S27_Vendor_Design_Changes
S27 — Vendor Design Changes (VDC) Register — Supplier-Initiated Changes
Tracks all supplier-initiated design changes — approval, risk, disposition ¦ Owner: Sourabh Tarodekar ¦ Linked ECOs in S26_Engineering_Change_Orders
VDC ID | Linked ECO | Supplier | Equip Ref | Change Description | Change Type | Supplier Reason | Notified Date | Customer Approval Req? | Risk Assessment | Disposition | Conditions | Requalif. Req? | Approval Date | Notes
VDC-001 | ECO-003 | Applied Materials | EQ-014 | CVD SiC edge ring material substitution (SiC density >=3.12 g/cm3 -> premium CVD SiC grade) | Function | Improved dimensional stability at high temp; supplier quality improvement | 2025-02-10 | YES | LOW — dimensional spec maintained; thermal improvement expected | ACCEPT — CONDITIONAL | Re-validate thermal profile; confirm +/-1.5% uniformity spec met | YES | 2025-02-28 | Triggered ECO-003; AMAT FSE on-site for re-validation
VDC-002 | — | Pfeiffer Vacuum | EQ-002 | Magnet assembly supplier change — from EU Tier-2 to Asian Tier-2 supplier (equivalent grade spec) | Form | Tier-2 supplier consolidation; cost reduction in Pfeiffer supply chain | 2025-03-05 | YES | HIGH — magnetic performance critical to TMP speed/accuracy | REJECT | Pfeiffer to provide full equivalency test data; re-submit with material certs | YES | — | REJECTED: insufficient test data provided. Pfeiffer re-submitting with test certs Q3-2025
VDC-003 | ECO-002 | Tokyo Electron Ltd | EQ-004 | PID zone controller firmware update v3.8 -> v4.0 — new thermal ramp algorithm | Fit/Function | TEL global platform update — improved uniformity for 65nm+ processes | 2025-03-20 | YES | LOW-MOD — algorithm change; verified by TEL at factory on identical system | ACCEPT — CONDITIONAL | Run 3-wafer PQ qualification lot before production release | YES | 2025-04-08 | TEL global platform upgrade; triggered ECO-002 for recipe B3 update
VDC-004 | — | Brooks Automation | EQ-005 | SCARA servo drive firmware update v2.3 -> v2.5 — improved torque compensation | Function | Bug fix — eliminates 0.05mm positional drift under thermal load | 2025-04-01 | NO | LOW — positional improvement; no form/fit change | ACCEPT | No requalification required; monitor 30-day performance after update | NO | 2025-04-08 | Brooks minor update; no qualification re-trigger required
VDC-005 | ECO-009 | Linde Engineering | EQ-008 | Pressure relief valve manufacturer change (same setpoint; different brand — Leser -> Emerson) | Form | Leser discontinuing model; Emerson equivalent specification | 2025-05-15 | YES | MOD — safety-critical component; must verify setpoint and certification | ACCEPT — CONDITIONAL | Provide Emerson PED certification and hydrostatic test report | YES | Pending | Triggered ECO-009 for pressure re-certification; Emerson certs received; review in progress
VDC-006 | — | Siemens AG | EQ-009 | TIA Portal software v18 -> v19 migration — new tag management structure | Fit | Siemens mandatory platform migration for security patch compatibility | 2025-06-10 | YES | LOW — software change; backward compatible; Siemens certified | ACCEPT | Apply per cybersecurity ECO-007 schedule; backup current config before update | NO | 2025-06-20 | Coordinated with ECO-007 cybersecurity update; Siemens migration guide followed
VDC-007 | — | Daikin Applied | EQ-012 | Refrigerant change R-410A -> R-454B (HFO blend) — regulatory compliance | Function | ASHRAE 34 update and EU F-Gas regulation phase-down of HFC refrigerants | 2025-07-01 | YES | MOD — different refrigerant chemistry; system pressure slightly lower; seals reviewed | ACCEPT — CONDITIONAL | Daikin to provide updated system performance data and seal compatibility certs | NO | Pending | Regulatory-driven; R-454B lower GWP. Daikin submitting updated commissioning data.
VDC SUMMARY
Total VDCs Logged
Accepted (incl. Conditional)
Rejected
Requalification Required

## S28_Yield_Production_Metrics
S28 — Yield & Production Metrics — OEE, Process Yield & Quality Tracking
OEE = Availability x Performance x Quality ¦ Yield target: 96% (S01 Assumptions) ¦ Owner: Sourabh Tarodekar ¦ Monthly reporting by process tool ¦ Feeds S29 ROI Tracker
Equip ID | Tool | Period | Availability (%) | Performance (%) | Quality Rate (%) | OEE (%) | Planned Yield (%) | Actual Yield (%) | Yield Variance (pp) | Units Produced | Units Scrapped | Scrap Rate (%) | Top Defect Mode | Corrective Action
EQ-003 | Tube Furnace — Thermco | Jul-2025 | 90.5% | 96% | 97.8% |  | 96% | 94.1% |  | 15200 | 890 |  | Zone 3 temp uniformity +/-1.8C | TEL FSE reviewed; zone 3 element replaced; uniformity now +/-1.2C
EQ-003 | Tube Furnace — Thermco | Aug-2025 | 92% | 97% | 98.3% |  | 96% | 95.8% |  | 16400 | 277 |  | Minor particle contamination — wafer edge | Cleaning protocol updated; edge exclusion improved
EQ-003 | Tube Furnace — Thermco | Sep-2025 | 93% | 97% | 98.7% |  | 96% | 96.6% |  | 17200 | 228 |  | Within spec — no dominant defect | No action required
EQ-004 | Batch Oxidation Furnace — TEL | Jul-2025 | 91% | 95.5% | 97.5% |  | 96% | 93.3% |  | 10800 | 270 |  | Batch loading uniformity — slot 1/24 variation | TEL batch loading algorithm updated; batch review at G4 gate
EQ-004 | Batch Oxidation Furnace — TEL | Aug-2025 | 91% | 96.5% | 97.8% |  | 96% | 94.1% |  | 11200 | 246 |  | Improving — loading fix effective | Monitor; target 95%+ OEE next period
EQ-004 | Batch Oxidation Furnace — TEL | Sep-2025 | 92% | 97% | 98.2% |  | 96% | 95.4% |  | 11850 | 195 |  | Minor recipe drift — within SPC control | SPC limits tightened; no action required
EQ-005 | SCARA Robot — Brooks (x6) | Jul-2025 | 93.5% | 98.5% | 99.9% |  | N/A | 95.6% | N/A | 62800 | 63 |  | Isolated pick error — Wrist B calibration | Calibration corrected; all 6 robots re-verified
EQ-005 | SCARA Robot — Brooks (x6) | Aug-2025 | 94.5% | 99% | 100% |  | N/A | 97.1% | N/A | 66200 | 0 |  | None — zero defects this period | No action required
EQ-005 | SCARA Robot — Brooks (x6) | Sep-2025 | 94% | 99% | 100% |  | N/A | 96.7% | N/A | 67100 | 0 |  | None | No action required
EQ-014 | RTP — Applied Materials (x2) | Jul-2025 | 93% | 97.5% | 98.3% |  | 96% | 95.9% |  | 8900 | 107 |  | Edge ring thermal non-uniformity — pre-ECO-003 | ECO-003 CVD SiC edge ring replacement — resolved
EQ-014 | RTP — Applied Materials (x2) | Aug-2025 | 93.5% | 98% | 99.1% |  | 96% | 97.1% |  | 9200 | 56 |  | Below spec — none; edge exclusion improved | ECO-003 effective; no action required
EQ-014 | RTP — Applied Materials (x2) | Sep-2025 | 94% | 98% | 99.3% |  | 96% | 97.3% |  | 9450 | 47 |  | Within spec — lamp uniformity nominal | AMAT lamp performance meeting spec; no action
PROGRAM OEE SUMMARY
OEE Target (Avail 92% x Perf 97% x Quality 96%)
Average Actual OEE (Process Tools, Q3-2025)
Yield Target (S01 Assumptions) | 96%
Average Actual Yield (Q3-2025)
Tools Below OEE Target this Period
Total Units Produced (Q3-2025)
Total Units Scrapped (Q3-2025)

## S29_Equipment_ROI_Tracker
S29 — Equipment ROI & Performance Tracker — Actual vs Plan (Post-Commissioning)
Program: Greenfield Expansion Phase II ¦ Populated after G5 Production Release ¦ 30-day / 90-day / 180-day checkpoints ¦ Actual inputs in BLUE ¦ Variances auto-calculated ¦ Planned values pulled from S02 (throughput/uptime) and S10 (capacity model)
Equipment ID | Equipment / Tool | Planned Throughput (u/hr) | Actual Throughput (u/hr) | Throughput Variance | Planned Uptime % | Actual Uptime % | Uptime Variance | Planned Annual Energy Cost | Actual Annual Energy Cost | Checkpoint | Status | Notes
EQ-003 | Tube Furnace — Thermco | 24 | 23 |  | 92% | 90.5% |  | 86944 | Pending | 30-Day | IN PROGRESS | Monitor zone temperature uniformity; recipe 3 showing 0.3% yield below target
EQ-004 | Batch Oxidation Furnace — TEL | 18 | 18 |  | 92% | 91% |  | 100672 | Pending | 30-Day | IN PROGRESS | TEL FSE reviewing batch loading algorithm; minor throughput shortfall under investigation
EQ-005 | SCARA Robot — Brooks (x6) | 120 | 118 |  | 92% | 93.5% |  | 3844 | Pending | 30-Day | ABOVE PLAN | Robot uptime exceeding plan. MES integration performing well. No action required.
EQ-014 | RTP — Applied Materials (x2) | 32 | 32 |  | 92% | 93% |  | 77792 | Pending | 30-Day | ABOVE PLAN | Edge ring yield at 97.2% vs 96% target. Lamp array performing well. No action.
EQ-001 | Dry Screw Vacuum Pump (x4) | N/A | Pending | — | 92% | 88% |  | 16931 | Pending | 90-Day | BELOW PLAN | Uptime below plan — bearing set replacement needed on pump 2. CR raised.
EQ-002 | Turbomolecular Pump — Pfeiffer (x3) | N/A | Pending | — | 92% | Pending | — | 10982 | Pending | 90-Day | PENDING | 90-day checkpoint pending. Safety stock in place.
EQ-006 | Overhead Conveyor — Daifuku | N/A | Pending | — | 92% | Pending | — | 20134 | Pending | 90-Day | PENDING | Track system performing nominally. Wi-Fi integration stable. No issues to date.
EQ-007 | Gas Handling Cabinet — Air Liquide (x4) | N/A | Pending | — | 92% | Pending | — | 732 | Pending | 90-Day | PENDING | Gas cabinet operational. MFC calibration rotation in schedule. No events.
EQ-009 | DCS — Siemens S7-1500 (x5) | N/A | Pending | — | 92% | Pending | — | 1098 | Pending | 180-Day | PENDING | DCS fully operational. Cybersecurity audit scheduled Month 4.
EQ-011 | Dry-Type Transformer (x2) | N/A | Pending | — | 99% | Pending | — | 0 | Pending | 180-Day | PENDING | Transformer operating within thermal limits. Cooling fans checked. No issues.
EQ-012 | Process Chiller — Daikin (x3) | N/A | Pending | — | 99% | Pending | — | 65525 | Pending | 180-Day | PENDING | Glycol loop stable. Compressor discharge pressure nominal. 180-day checkpoint due.
EQ-015 | AMR Fleet — MiR (x10) | N/A | Pending | — | 92% | Pending | — | 5491 | Pending | 180-Day | PENDING | Fleet routing optimisation Phase 2 scheduled Month 5. Battery health nominal.
POST-COMMISSIONING PERFORMANCE SUMMARY
Equipment Platforms Tracked
Platforms with 30-Day Data
Platforms Above or On Plan
Platforms Below Plan
Platforms Pending Data

## S30_Executive_Dashboard
S30 — CAPEX PROGRAM EXECUTIVE DASHBOARD
Program: Greenfield Expansion Phase II · Program Manager: Sourabh Tarodekar · AR Reference: AR-2025-0082 · Status as of: 2025-Q3 · All values linked live from program model sheets (S01-S32)
KEY PERFORMANCE INDICATORS — PROGRAM SNAPSHOT
TOTAL CAPEX PORTFOLIO |  | APPROVED PROGRAM BUDGET |  | 10-YR NPV (vs Min-CapEx) |  | ESTIMATED IRR |  | ANNUAL ENERGY COST
Equipment + Installation (USD) |  | Incl. contingency + FX reserve (USD) |  | Scenario B vs A — 8% WACC (USD) |  | 10-yr, vs 8.0% hurdle rate |  | Full portfolio (USD/yr)
ANNUAL PRODUCTION CAPACITY |  | BASELINE UTILIZATION |  | SUPPLY CHAIN RISK INDEX |  | PROGRAM % COMPLETE |  | OPEN PROGRAM BLOCKERS
Process tools (units/yr) |  | Baseline Demand / Capacity |  | Avg Composite Risk Score |  | Avg milestone completion |  | Across all gates
CAPEX & FINANCIAL METRICS |  |  |  |  | SUPPLY CHAIN & SUPPLIER RISK
Metric | Value | Source Sheet |  |  | Metric | Value | Source Sheet
Total Equipment Purchase Cost |  |  | S02_Equipment_Portfolio |  | Avg Supplier Lead Time (wks) |  |  | S03 — Current market avg
Total Installation Cost |  |  | S02_Equipment_Portfolio |  | Avg Lead Time Delta vs Standard (wks) |  |  | S03 — Market vs standard LT
Total CapEx (Equip + Install) |  |  | S02 — Formula |  | Avg Supplier Reliability Score |  |  | S03 — 100-point scale
Contingency Reserve (10%) |  |  | S12_AR_Summary |  | Avg Composite Risk Score |  |  | S03 — Risk Score formula
FX Hedge Reserve |  |  | S12_AR_Summary |  | Max Risk Score (Worst Supplier) |  |  | S03 — Highest risk item
NRE + Program Management |  |  | S12_AR_Summary |  | Single-Source Components |  |  | S03 — RED flag items
TOTAL APPROVED BUDGET |  |  | S12_AR_Summary |  | HIGH Risk Tier Suppliers |  |  | S03 — Weekly exec review
10-Yr NPV vs Min-CapEx (Sc B-A) |  |  | S13_Scenario_Analysis |  | CRITICAL Risk Items (S16 model) |  |  | S16 — Escalated items
Estimated IRR (10-yr) |  |  | S13_Scenario_Analysis |  | HIGH Risk Items (S16 model) |  |  | S16 — Senior mgr review
Payback Period (yrs) | 4.2 |  | S13_Scenario_Analysis |  | Components with Buffer Stock |  |  | S16 — In-stock safety items
CAPACITY & EQUIPMENT PERFORMANCE |  |  |  |  | PROGRAM SCHEDULE & CONTROL
Metric | Value | Source Sheet |  |  | Metric | Value | Source Sheet
Total Equipment Platforms |  |  | S02 — Full portfolio |  | Critical Path Duration (weeks) |  |  | S07 — Max EF
Annual Production Capacity |  |  | S10 — Process tools only |  | Critical Path Items |  |  | S07 — Zero float items
Baseline Demand | 750000 |  | S11 — Current program target |  | HIGH/CRITICAL Risk Deploy. Items |  |  | S09 — Risk-flagged equip.
Baseline Utilization |  |  | S10 — Demand / Capacity |  | Total Milestones |  |  | S25 — Full program scope
Capacity Cushion (units/yr) |  |  | S10 — Headroom above demand |  | Milestones Complete |  |  | S25 — Formally closed
Surge Demand Scenario (+20%) | 900000 |  | S11 — Stress test |  | Milestones At Risk or Blocked |  |  | S25 — Require PM action
Annual Energy Cost (all equip.) |  |  | S02 — Formula linked |  | Gates Formally Approved |  |  | S25 — G0-G5 gates
Total Spare Parts Inventory Value | $124,200 |  | S23 — Stock x unit cost |  | Open Blockers Across All Gates |  |  | S25 — Must = 0 before gate
PROGRAM HEALTH SCORECARD
Health Dimension | Current Value | Target / Threshold | RAG Status | Action Required
Budget Control | 5.8% | <50% contingency used | AMBER | Monitor change requests; contingency intact at ~5.8% used
CapEx Financial Return (NPV) |  | >$5M NPV vs Min-CapEx | GREEN | No action — Scenario B NPV confirmed by Finance model
Supply Chain Risk |  | Avg Risk Score < 10 | AMBER | EQ-002 Pfeiffer single-source CRITICAL — alt vendor qual underway; escalate weekly
Schedule / Critical Path |  | <2 zero-float items | RED | Multiple items with zero float; daily PM tracking required
Capacity Headroom |  | Utilization < 90% | GREEN | Baseline utilization well below threshold; adequate headroom
Program Milestone Progress |  | >30% complete by Wk 10 | AMBER | Milestones at risk require PM attention; others tracking to plan
Yield / OEE Performance |  | OEE >= ~86% target | GREEN | Process tools performing at or above OEE target
CapEx Program Management Model · All KPIs linked live from S01-S32 · Model prepared by: Sourabh Tarodekar, Program Manager · Workbook contains 33 sheets across 6 zones, 15 equipment platforms · For Finance / Engineering Leadership use only · CONFIDENTIAL

## S31_Vendor_Scorecard
S31 — Vendor Scorecard & Qualification Status — CapEx Equipment Suppliers
Scores suppliers on delivery, quality, commercial, technical, and support dimensions ¦ Qualification stage tracks RFI -> RFQ -> AVL (Approved Vendor List) ¦ Inputs in BLUE
SCORING DIMENSION WEIGHTS
Dimension | Weight | Description
Delivery Performance (On-Time %) | 25% | Historical on-time delivery rate vs committed dates
Quality (Defect Rate / FAT Pass Rate) | 20% | First-pass FAT acceptance rate; incoming inspection defect rate
Commercial (Pricing Competitiveness) | 20% | Benchmark vs market; responsiveness; payment terms
Technical Capability (Spec Compliance) | 25% | Meets or exceeds technical specification; engineering support quality
Program Support (Communication / PM) | 10% | Responsiveness; dedicated PM; escalation handling
SUPPLIER SCORECARD & QUALIFICATION MATRIX
Supplier | Equip Ref | Region | Qual Stage | Delivery (1-5) | Quality (1-5) | Commercial (1-5) | Technical (1-5) | Program Support (1-5) | Composite Weighted Score | Supplier Status | Last Audit Date | Next Review Date | Qualification Notes
Edwards Vacuum | EQ-001 | UK | AVL — Approved | 4 | 4 | 3 | 4 | 4 |  | APPROVED | 2025-Q1 | 2025-Q3 | Reliable supplier; post-Brexit logistics occasionally impacts lead time; alt-vendor qual complete
Pfeiffer Vacuum | EQ-002 | DE | AVL — Conditional | 3 | 5 | 3 | 5 | 3 |  | CONDITIONAL | 2024-Q3 | 2025-Q2 | Single-source; HIGH supply risk. Conditional approval pending Shimadzu alt qualification.
Thermco Systems | EQ-003 | USA | AVL — Preferred | 5 | 5 | 4 | 5 | 5 |  | PREFERRED | 2024-Q4 | 2025-Q4 | Best-in-class performance; strong PM support; BTU validated as alt; no concerns
Tokyo Electron Ltd (TEL) | EQ-004 | JP | AVL — Preferred | 4 | 5 | 3 | 5 | 4 |  | PREFERRED | 2024-Q3 | 2025-Q3 | Premium supplier; higher commercial cost justified by TCO model; JPY FX hedged
Brooks Automation | EQ-005 | USA | AVL — Approved | 4 | 4 | 4 | 4 | 4 |  | APPROVED | 2025-Q1 | 2025-Q3 | Strong delivery and quality; MES integration complexity is program risk not supplier risk
Daifuku | EQ-006 | JP | AVL — Conditional | 3 | 4 | 3 | 4 | 3 |  | CONDITIONAL | 2024-Q4 | 2025-Q2 | Single-source for overhead track; commercial score impacted by $85K change order risk
Air Liquide Engineering | EQ-007 | FR | Qualification In Progress | 3 | 3 | 3 | 4 | 3 |  | IN QUALIFICATION | N/A | 2025-Q2 | Quote still under negotiation; hazmat permit risk reduces score; full audit scheduled Q2
Linde Engineering | EQ-008 | DE | AVL — Approved | 4 | 4 | 4 | 4 | 4 |  | APPROVED | 2024-Q3 | 2025-Q4 | Strong supplier; existing site gas supply contract provides leverage
Siemens AG | EQ-009 | DE | AVL — Preferred | 5 | 5 | 4 | 5 | 5 |  | PREFERRED | 2024-Q2 | 2025-Q4 | Strategic preferred supplier; highest reliability score in portfolio
Inductive Automation | EQ-010 | USA | AVL — Approved | 5 | 5 | 5 | 4 | 4 |  | APPROVED | 2024-Q4 | 2025-Q4 | Software vendor; excellent support; low supply risk
ABB Ltd | EQ-011 | CH | AVL — Approved | 4 | 4 | 4 | 4 | 4 |  | APPROVED | 2024-Q3 | 2025-Q4 | Established supplier; transformer lead time extended but within program tolerance
Daikin Applied | EQ-012 | JP | AVL — Approved | 4 | 4 | 3 | 4 | 4 |  | APPROVED | 2024-Q4 | 2025-Q3 | Solid supplier; glycol loop interface must be finalized before FAT — see CR-012
Busch Vacuum | EQ-013 | DE | AVL — Approved | 4 | 4 | 4 | 4 | 4 |  | APPROVED | 2024-Q3 | 2025-Q4 | Strong alt to Edwards for pump systems; validated as secondary source
Applied Materials (AMAT) | EQ-014 | USA | AVL — Preferred | 4 | 5 | 3 | 5 | 5 |  | PREFERRED | 2024-Q2 | 2025-Q4 | Strategic OEM relationship; highest-value PO in program; excellent technical support
Mobile Industrial Robots (MiR) | EQ-015 | DK | AVL — Approved | 4 | 4 | 4 | 4 | 3 |  | APPROVED | 2025-Q1 | 2025-Q3 | Strong fleet management platform; PM support slightly below average
Shimadzu Corp (Alt EQ-002) | EQ-002 | JP | Qualification In Progress | N/A | N/A | N/A | 3 | N/A | — | IN QUALIFICATION | N/A | 2025-Q3 | Initiated as alt to Pfeiffer per CR-007; TMP-3203L under technical evaluation; 90-day qual program
BTU International (Alt EQ-003) | EQ-003 | USA | AVL — Approved | 4 | 4 | 4 | 4 | 4 |  | APPROVED | 2024-Q2 | 2025-Q4 | Pre-qualified as secondary to Thermco; compatible process performance; available as backup
Matheson Gas (Alt EQ-007) | EQ-007 | USA | RFQ Issued | N/A | N/A | 3 | 3 | N/A | — | MONITORING | N/A | 2025-Q2 | RFQ issued as alternative to Air Liquide; pricing and delivery terms under review
VENDOR QUALIFICATION SUMMARY
Total Suppliers Tracked
Preferred Suppliers (AVL)
Approved Suppliers (AVL)
Conditional / Monitoring
In Qualification
Avg Composite Score (Active AVL)

## S32_Change_Tracker
S32 — Engineering Change Management Tracker — CapEx Phase II Program
All scope, technical, or budget changes must be logged here ¦ Approved changes flow to AR update and decision log ¦ Owner accountable for implementation
Change ID | Raised Date | Equipment Ref | Change Category | Change Description | Reason / Trigger | Cost Impact (USD) | Schedule Impact (wks) | Quality/Tech Risk | Raised By | Approved By | Change Status | Implementation Notes
CR-001 | 2025-03-17 | EQ-004 | Installation Scope | Add external 50-tonne crane hire and structural floor reinforcement for EQ-004 batch furnace installation | Site walk revealed existing 3.5T facility crane is insufficient for 4,800 kg TEL furnace. Structural analysis confirmed floor reinforcement required. | 62000 | 1 | LOW | T. Okonkwo (Facilities) | PM — Sourabh Tarodekar | APPROVED — IMPLEMENTED | Crane booked. Structural work complete Week 14. Cost added to EQ-004 install line item.
CR-002 | 2025-03-19 | EQ-001 | Facility Infrastructure | Install new 100A dedicated electrical sub-panel and 35m cable run for EQ-001 vacuum pump set | Existing electrical panel headroom 45 kW — insufficient for 4-pump set requiring 74 kW. Identified during site walk. | 22000 | 0 | LOW | T. Okonkwo (Facilities) | PM — Sourabh Tarodekar | APPROVED — IMPLEMENTED | Sub-panel installed Week 28-29. Electrical test passed. No schedule impact to EQ-001 delivery.
CR-003 | 2025-03-24 | EQ-007 | Regulatory / Compliance | Engage regulatory consultant for expedited hazmat permit for EQ-007 toxic gas cabinet | Standard permit lead time 8-12 weeks exceeds program schedule allowance of 6 weeks. Permit is on critical path. | 8500 | 0 | HIGH | D. Walsh (EHS) | PM — Sourabh Tarodekar | APPROVED — PENDING | Consultant engaged 2025-03-25. Permit application filed. Estimated approval 2025-05-30. Monitor weekly.
CR-004 | 2025-04-14 | EQ-003 | Technical Specification | Add helium leak test to EQ-003 tube furnace FAT protocol per site safety standard SHE-042 | Quality review identified omission of He leak test in Thermco-supplied FAT protocol. SHE-042 mandates He leak testing. | - | 0 | LOW | K. Tanaka (Quality) | Quality Director | APPROVED — IMPLEMENTED | FAT protocol updated and approved by Quality 2025-04-18. No cost or schedule impact.
CR-005 | 2025-04-21 | EQ-014 | Process Specification | Add edge ring qualification lot (25 wafers) to EQ-014 AMAT RTP FAT protocol | Process engineering identified edge-to-center non-uniformity risk at high ramp rates (>150C/s). | - | 0 | MODERATE | M. Chen (Process Eng.) | Director of Engineering | APPROVED — IMPLEMENTED | Protocol updated. 25-wafer edge ring lot included in FAT scope. No cost impact — AMAT absorbs wafer cost.
CR-006 | 2025-05-05 | EQ-006 | Schedule Change | Freeze Daifuku overhead conveyor layout by Week 6 — activate change control for any post-freeze deviation | Daifuku contract specifies 4-week delay + $85K re-engineering fee for any layout change after civil interface freeze. | - | 0 | MODERATE | Sourabh Tarodekar (PM) | PM — Sourabh Tarodekar | APPROVED — IMPLEMENTED | Freeze notice issued 2025-05-07. Layout confirmed by all teams. Change control process active.
CR-007 | 2025-05-05 | EQ-002 | Supplier Change | Initiate parallel qualification of Shimadzu TMP-3203L as alternative to Pfeiffer EQ-002 turbomolecular pump | EQ-002 is single-source with Pfeiffer. Risk accepted with condition of parallel alt vendor qualification. | 45000 | 0 | HIGH | S. Kim (Supply Chain) | VP Supply Chain | UNDER REVIEW | Shimadzu evaluation plan drafted. Test units requested. Qualification target: 90 days from Week 10 start.
CR-008 | 2025-05-05 | EQ-004 | Technical Specification | Execute JPY/USD forward currency hedge for EQ-004 TEL batch furnace ($1.36M JPY-denominated) | EQ-004 invoiced in JPY. Finance modelled adverse scenario at 142 JPY/USD — $64K additional cost. | - | 0 | LOW | R. Patel (Finance) | CFO | APPROVED — IMPLEMENTED | Forward contract executed 2025-05-08. Rate locked at 149.0 JPY/USD through Q4-2025.
CR-009 | 2025-05-12 | EQ-009 | Software / Integration | Add IT/OT DMZ network infrastructure to CapEx scope to support SCADA cybersecurity compliance | IT/OT review identified requirement for demilitarised zone (DMZ) per InfoSec policy OT-SEC-003. | 45000 | 0 | MODERATE | P. Singh (IT/OT) | PM — Sourabh Tarodekar | UNDER REVIEW | Network design spec in progress. Decision required by Week 15 to avoid impact to SCADA commissioning.
CR-010 | 2025-05-12 | EQ-005 | Software / Integration | Engage Brooks Automation software engineer on-site from Week 32 for MES/SEMI E30 software customisation | Manufacturing review confirmed SEMI E30 compliance required for fab MES interface. | 28000 | 0 | MODERATE | A. Novak (Manufacturing) | Director of Engineering | APPROVED — PENDING | Brooks SE engagement confirmed. MES command set document due Week 28. T&E budget allocated.
CR-011 | 2025-05-19 | EQ-013 | Technical Specification | Update EQ-013 Roots blower installation sequence — must install after EQ-001 dry screw pumps | Engineering review confirmed Roots blower (EQ-013) must be installed downstream of dry screw pumps (EQ-001). | - | 0 | LOW | M. Chen (Process Eng.) | Director of Engineering | APPROVED — IMPLEMENTED | Deployment timeline (S09) updated. Install sequence constraint documented in engineering notes.
CR-012 | 2025-05-19 | EQ-012 | Facility Infrastructure | Finalize glycol loop design for EQ-012 process chiller — complete engineering package by Week 14 | Mechanical engineering review confirmed glycol loop interface design must be finalized before Daikin FAT drawings. | - | 1 | MODERATE | T. Okonkwo (Facilities) | PM — Sourabh Tarodekar | UNDER REVIEW | Mechanical engineering team completing glycol loop design. Review meeting scheduled Week 13.
CHANGE IMPACT SUMMARY
Total Change Requests Logged
Approved and Implemented
Approved Pending Implementation
Total Under Review
Cumulative Cost Impact (USD)
Schedule Impact (wks)
HIGH or CRITICAL Budget Risk
Contingency Reserve Used (vs S12 AR Contingency Reserve)